## All Site Info
Site/Station Name (Name on Contract) | Public Station Name | Grid Cell ID | NWS LI ID | Part of NMP? | Land Ownership Category | Landownership Detail | Site Type (New, Existing, Existing - Moved > 100 ft) | Latitude | Longitude | Elevation | County | State | Ownership | Station Status | Station Status Note | Project Year (PY) | Installation Task Order & Fiscal Year | Installation Task Order Date Award | Contract Installation Deadline | O&M Period of Performance | Cultural Survey & Sec 106 Responsible Party | Section 106 Status | NEPA Status (Date REC Signed) | NRCS Soil Survey | Candidate Site Form_Site Report- Date Received | Station Report - Date Received | Annual Report - Date Received | Equipment Installation Complete | Data Transmitting | NOTES
Wetzel NE | Wetzel NE | A-01 | WETM8 |  | Private on Tribal Lands | Blackfeet Indian Reservation | New | 48.7795 | -113.1185 | 4459 | Glacier | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-26 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-10-13 | 2024-09-30
Dog Gun Lake E | Dog Gun Lake E | A-02 | DOGM8 |  | Tribal Lands | Blackfeet Indian Reservation | New | 48.3778 | -113.0621 | 4836 | Glacier | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-10-15 | 2024-09-30
Dillon |  | A-12 |  |  | Private | Private | New | 45.2694 | -112.5087 | 5271 | Beaverhead | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY26) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Fort Yates 2W |  | AA-10 | FYTN8 |  | Tribal Lands | Standing Rock Sioux Tribe (Sitting Bull College) | Existing - Moved > 100ft (670 ft) | 46.0846 | -100.6792 | 1786 | Sioux | North Dakota | NDAWN | Removed | Install 2025 | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress |  | 2023-09-13
Strasburg 15W | Strasburg 15W | AA-10 | SSBN8 | N | Private | Private | New | 46.1154 | -100.4715 | 1877 | Emmonds | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO7 ND (FY25) | 2025-08-13 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-11 | 2025-02-21 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Mobridge 8WSW |  | AA-12 |  |  | Private on Tribal Lands | Standing Rock Reservation | New | 45.4878 | -100.5773 |  | Corson | South Dakota | SD Mesonet | Removed | Submitted as candidate site Nov 2021; Pending Issues | Unk | Unk. Timeline |  |  |  | USACE Staff | Complete | Complete
Ridgeview 8ENE | La Plant | AA-13 | LPMS2 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.1455 | -100.673 | 2001 | Dewey | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) | 2024-09-04 | 2024-09-30 | 2025-09-30 | Tribe | Complete | Complete | 2024-10-07 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-09-06 | 2024-09-30
Mission Ridge 14SSE |  | AA-15 |  |  | Private | private | New | 44.4939 | -100.6937 | 2061 | Stanley | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY6 | TO10 SD (FY26) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE Staff | Complete | Complete
Fort Pierre 6WSW |  | AA-16 |  |  | Private | private | New | 44.3213 | -100.4756 | 1801 | Stanley | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY6 | TO10 SD (FY26) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE Staff | Complete | Complete
Murdo 9NNW |  | AA-17 |  |  | Private | private | New | 44.0106 | -100.7678 | 2246 | Jones | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY6 | TO10 SD (FY26) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
White River | White River | AA-18 | WRIS2 |  | City | Non-federal airport property | Existing - Moved > 100ft | 43.5586 | -100.7423 | 2140 | Mellette | South Dakota | SD Mesonet | Complete | Installed in 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE | Complete | Complete 9/10/2021 | 2022-06-09 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-11-24 | 2021-12-15
Rosebud | Rosebud | AA-19 | RBMS2 |  | Tribal Lands | Rosebud Sioux Tribe | Existing | 43.2002 | -100.7208 | 2808 | Todd | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | Rosebud Tribe | Complete | Complete 8/5/2021 | 9/1/2022 (Orig. Sampling in 2019) | n/a | 2024-02-28 | 2024-02-28 | 2022-07-26 | 2022-08-20
Kilgore 5E | Kilgore 5E | AA-20 | KLGN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.9196 | -100.8578 | 2844 | Cherry | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-24 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey. Bald & Golden Eagle Protection Act - Should a bald or golden eagle nest be detected within 0.5 miles of the project site prior to installation, USACE shall be contacted, and the National Bald and Golden Eagle Management Guidelines (FWS, 2007) will be followed.
Crookston 17S | Crookston 17S | AA-21 | COON1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.6948 | -100.8384 | 2894 | Cherry | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-13 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey. Bald & Golden Eagle Protection Act - Should a bald or golden eagle nest be detected within 0.5 miles of the project site prior to installation, USACE shall be contacted, and the National Bald and Golden Eagle Management Guidelines (FWS, 2007) will be followed.
Picardville 6SW | Picardville 6SW | AA-6 | PCKN8 | N | Private | Private | New | 47.4154 | -100.673 | 1896 | Sheridan | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-22 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-07-17 | 2024-09-30 | FPPA Form submitted to NRCS; ENV. - Dakota Skipper - If habitat is determined to be present by surveys conducted in the summer of 2023, occupancy surveys shall be conducted by a USFWS permitted surveyor following the 2022 Dakota Skipper Survey Protocol.; ENV. - USFWS Wetland easement - site installation and access avoids wetlands. No SUP needed.
Wing | Wing | AA-7 | WNGN8 | N | Private | Private | New | 47.2719 | -100.3303 | 1973 | Burleigh | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-05-19 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-05-10 | 2023-09-30
McKenzie 2E | McKenzie 2E | AA-8 | MCKN8 | N | Private | Private | New | 46.8222 | -100.3617 | 1773 | Burleigh | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-22 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-09-13 | 2023-09-30
Livona 5S | Livona 5S | AA-9 | LIVN8 | N | Private | Private | New | 46.4359 | -100.5677 | 1690 | Emmonds | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-26 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-05-22 | 2024-09-30
Linton | Linton | AB-10 | LINN8 | Y | Private | Private | Existing | 46.3268 | -100.2809 | 1966 | Emmons | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-09 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023-06-28 | 2023-09-30
Herreid 2NNW | Herreid | AB-11 | HRMS2 | N | Private | Private | New | 45.8664 | -100.0909 | 522 | Campell | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2024-10-03 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-07 | 2024-11-30
Mound City 4SSW | Mound City | AB-12 | MCMS2 |  | Private - Easement | FWS Easement for Sand Lake Wetland Management District; FPPA Prime Farmland | Existing | 45.6715 | -100.1148 | 1746 | Campbell | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE | Complete | 2022-08-31 | 2023-07-26 | 2022-11-15 | 2024-02-28 | 2024-02-28 | 2023-08-10 | 2023-09-30
Lowry 2S | Lowry | AB-13 | LRMS2 |  | Private | Private | New | 45.2816 | -99.9774 | 2104 | Walworth | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-24 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-08-10 | 2023-09-30
Gettysburg 14W | Gettysburg W | AB-14 | GWMS2 | N | Private | Private | New | 45.0057 | -100.2423 | 570 | Potter | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2024-10-03 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-08 | 2024-11-30
Onida 13WSW | Onida | AB-15 | ONMS2 |  | Private on Tribal Lands | Crow Creek Indian Reservation; FPPA Prime Farmland | New | 44.6463 | -100.3202 | 1757 | Sully | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE | Complete | Complete | 2022-10-13 | 2022-08-27 | 2024-02-28 | 2024-02-28 | 2022-11-02 | 2022-09-30
Blunt 11S | Pierre | AB-16 | PIMS2 |  | State | South Dakota State Univeristy | New | 44.3541 | -99.9997 | 1762 | Hughes | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-05 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-05-03 | 2024-09-30
Vivian 6NNW |  | AB-17 |  | No | Private | Private | New | 44.0127 | -100.3244 | 619 | Lyman | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Vivian 12S | Vivian | AB-18 | VVMS2 |  | Private | Private | New | 43.7508 | -100.2963 | 1919 | Lyman | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-14 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-08-02 | 2023-09-30
Carter 6SSW |  | AB-19 |  | N | Tribal Lands | Rosebud Sioux Tribe | New | 43.3163 | -100.2531 | 2328 | Todd | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-26
Sparks 3E | Sparks 3E | AB-20 | SKSN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.9592 | -100.2093 | 2857 | Cherry | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-10 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey.
Wood Lake 3SE | Wood Lake 3SE | AB-21 | WDLN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.6139 | -100.1996 | 2669 | Cherry | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-01 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey. Bald & Golden Eagle Protection Act - Should a bald or golden eagle nest be detected within 0.5 miles of the project site prior to installation, USACE shall be contacted, and the National Bald and Golden Eagle Management Guidelines (FWS, 2007) will be followed.
Hurdsfield NW | Hurdsfield NW | AB-6 | HDFN8 | N | Private | Private | New | 47.4511 | -99.9372 | 1903 | Wells | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-20 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-07-30 | 2024-09-30 | ENV. - USFWS Wetland easement - site installation and access avoids these wetlands. No SUP needed.
Robinson | Robinson | AB-7 | ROBN8 | Y | Private | Private | Existing | 47.173 | -99.7982 | 1829 | Kidder | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | 2021-02-08 | 2021-08-18 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-08-05 | 2021-11-19
Steele | Steele | AB-8 | SEEN8 | Y | Private | Private | Existing | 46.894 | -99.9927 | 1862 | Kidder | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-09-29 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-09-23 | 2022-09-28
Kintyre 3S | Kintyre 3S | AB-9 | KYTN8 | N | Private | Private | New | 46.5013 | -99.9689 | 1958 | Emmons | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-11 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Wishek | Wishek | AC-10 | WISN8 | Y | Private | Private | Existing | 46.2599 | -99.6658 | 2219 | McIntosh | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-08-26 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-08-15 | 2022-09-28
Zeeland | Zeeland | AC-11 | ZELN8 | Y | Private | Private | Existing | 46.0133 | -99.6877 | 2070 | McIntosh | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-08-26 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-08-16 | 2022-09-28
Bowdle | Bowdle | AC-12 | BWLS2 |  | City | Non-federal airport property | Existing | 45.4388 | -99.6733 | 1965 | Edmunds | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-05-01 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-10 | 2021-12-15
Onaka 4NNW |  | AC-13 |  |  | Private | private | New | 45.245 | -99.4815 | 1878 | Edmunds | South Dakota | SD Mesonet | Removed | Submitted as candidate site Oct 2021; Pending Landowner issues | Unk | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Harrold 8NW | Harrold | AC-15 | HDMS2 | N | Private | Private | New | 44.6109 | -99.8298 | 506 | Sully | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-18 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-08-08 | 2025-09-30
Lower Brule 2WNW | Lower Brule | AC-16 | LBMS2 |  | Private | Private | New | 44.0822 | -99.6111 | 1777 | Lyman | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | Tribe | Complete | 2022-08-31 | 2023-08-29 | 2022-11-15 | 2024-02-28 | 2024-02-28 | 2023-05-25 | 2023-09-30
Kennebec 6SSE | Kennebec | AC-17 | KBMS2 |  | Private | Private | New | 43.816 | -99.8254 | 1772 | Lyman | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-17 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-08-01 | 2023-09-30
Hamill | Hamill | AC-18 | HMLS2 |  | Private | Private | Existing | 43.5938 | -99.7122 | 1863 | Tripp | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 6/24/2022 (Orig. Sampling in 2019) | n/a | 2024-02-28 | 2024-02-28 | 2022-07-14 | 2022-08-20
Colome 4NNE | Winner | AC-19 | WNMS2 |  | Private | Private | New | 43.3141 | -99.693 | 2097 | Tripp | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-05-25 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-05-17 | 2023-09-30
Springview 2W | Springview 2W | AC-20 | SVWN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.8282 | -99.7958 | 2461 | Keya Paha | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-30 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey.
Ainsworth 5N | Ainsworth 5N | AC-21 | AINN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.6144 | -99.8466 | 2502 | Brown | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-09 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey.
Bremen 3W | Bremen 3W | AC-5 | BMRN8 | N | Private | Private | New | 47.7458 | -99.3184 | 1563 | Wells | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-19 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-07-31 | 2024-09-30 | FPPA Form submitted to NRCS
Heaton 1S | Heaton 1S | AC-6 | HEAN8 | N | City | Heaton Township | New | 47.4619 | -99.544 | 1725 | Wells | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-29 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Tappen 3E | Tappen 3E | AC-7 | TAPN8 | Y | Private | Private | Existing - Moved < 50 ft | 46.8855 | -99.5751 | 1833 | Kidder | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-31 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Streeter | Streeter | AC-8 | STRN8 | Y | University | NDSU | Existing | 46.718 | -99.4608 | 1992 | Kidder | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-19 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-07-20 | 2021-11-19
Neudorf 10SW | Neudorf 10SW | AC-9 | NDFN8 | N | Private | Private | New | 46.5001 | -99.3664 | 1956 | Logan | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-09 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Wirch 7NW | Wirch 7NW | AD-10 | WRHN8 | N | Private | Private | New | 46.1432 | -99.0659 | 1971 | McIntosh | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-05-22 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-05-07 | 2024-09-30
Long Lake 4NW | Long Lake | AD-11 | LLMS2 | N | Private | Private | New | 45.9066 | -99.2554 | 613 | McPherson | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE Contractor | Complete | 2022-08-31 | 2025-06-26 | 2022-10-15 | 2025-11-15 | 2025-12-03 | 2025-09-07 | 2025-09-30 | Nathan Edwards sent updated location on 4/18/24
Ipswich 5SSW |  | AD-12 |  |  | Private | private | New | 45.3759 | -99.0707 | 1553 | Edmunds | South Dakota | SD Mesonet | Removed | Submitted as candidate site Oct 2021; Pending Landowner issues | Unk | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Seneca 15SSE | Highmore N | AD-14 | HMMS2 |  | Private | private | New | 44.8572 | -99.4144 | 1921 | Hyde | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-09 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-07-10 | 2024-09-30
Highmore | Highmore | AD-15 | HIHS2 |  | State | South Dakota State - University Reseach Farm | Existing | 44.5256 | -99.4601 | 1879 | Hyde | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2019-06-19 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-22 | 2021-12-23
Gann Valley 9WNW |  | AD-16 |  |  | Private | Private | New | 44.0788 | -99.1576 | 1642 | Buffalo | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-15
Oacoma | Oacoma | AD-17 | OCMS2 |  | Private | Private | Existing | 43.7982 | -99.4156 | 1443 | Lyman | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2019-07-02 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-04 | 2021-11-19
Iona 5S | Gregory N | AD-18 | GRMS2 |  | Private | Private | New | 43.4642 | -99.439 | 1932 | Gregory | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-12 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-05-23 | 2024-09-30
Dallas 7S | Gregory | AD-19 | GGMS2 |  | Private | Private | New | 43.1374 | -99.4933 | 2189 | Gregory | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-05-26 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-05-17 | 2023-09-30
Burton 7E |  | AD-20 | BTMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.924 | -99.4452 | 617.67 | Keya Paha | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Bassett 8N | Bassett 8N | AD-21 | BATN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.7006 | -99.4979 | 2133 | Rock | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-17 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey. Bald & Golden Eagle Protection Act - Should a bald or golden eagle nest be detected within 0.5 miles of the project site prior to installation, USACE shall be contacted, and the National Bald and Golden Eagle Management Guidelines (FWS, 2007) will be followed.
Carrington | Carrington | AD-6 | CRGN8 | Y | University | NDSU | Existing | 47.5086 | -99.1323 | 1561 | Foster | North Dakota | NDAWN | Complete | Install 2021 | na | Not on USACE Task Order | na | na | na |  | na | na | na | na | na | na | 2020 | 2021-11-19
Woodworth 2NE | Woodworth 2NE | AD-7 | WDHN8 | N | Private | Private | New | 47.154 | -99.2687 | 1957 | Stutsman | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-04 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Jamestown | Jamestown | AD-8 | JSTN8 | Y | Private | Private | Existing | 46.9064 | -98.9274 | 1639 | Stutsman | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2/8/2021 | 2022-09-29 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-09-16 | 2022-09-28
Jud 1S | Jud 1S | AD-9 | JUNN8 | N | Private | Private | New | 46.5151 | -98.8918 | 1728 | LaMoure | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-01 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Ellendale 4NE | Ellendale 4NE | AE-10 | ELDN8 | N | Private | Private | New | 46.0529 | -98.4953 | 1459 | Dickey | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-24 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Leola | Leola | AE-11 | LLAS2 |  | Private | Private | Existing | 45.7165 | -98.9311 | 1571 | McPherson | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2019-05-01 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-10 | 2021-12-15
Mina 4ESE | Aberdeen W | AE-12 | AWMS2 | N | Private | Private | New | 45.4054 | -98.6834 | 425 | Brown | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2024-10-03 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-22 | 2024-11-30
Chelsea 6S |  | AE-13 |  |  | Private | private | New | 45.0847 | -98.7433 | 1351 | Faulk | South Dakota | SD Mesonet | Removed | Submitted as candidate site Oct 2021; Pending Landowner issues | Unk | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Rockham 6SSE | Rockham | AE-14 | RHMS2 |  | Private | Private | New | 44.8223 | -98.7965 | 1365 | Hand | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-28 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-06-06 | 2024-09-30
Wessington 3W | Wessington | AE-15 | WGMS2 |  | Private - Easement | NRCS Conservation Reserve Program | New | 44.4592 | -98.7614 |  | Hand | South Dakota | SD Mesonet | Complete | Submitted as candidate site Oct 2021; Resubmitted with new location | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-03 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-07-03 | 2024-09-30 | FPPA Site - Score >160; AD-1006 form submitted
Gann Valley 5ENE |  | AE-16 |  |  | Private | Private | New | 44.057 | -98.8868 | 1694 | Jerauld | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-01
White Lake | White Lake | AE-17 | WTES2 |  | Private | Private | Existing | 43.7372 | -98.6936 | 1637 | Aurora | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 3/7/2021 | 8/19/2022 (Orig. Sampling in 2019) | n/a | 2024-02-28 | 2024-02-28 | 2022-07-27 | 2022-08-20
Platte 15WNW | Academy | AE-18 | ACMS2 | N | Private | Private | New | 43.4992 | -99.0929 | 529 | Charles Mix | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2024-10-03 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-15 | 2024-11-30
Boyd 2 | Naper 2W | AE-20 | NARN1 | N | State | State Educational Lands and Funds - Leased Public | New | 42.9663 | -99.1388 | 2105 | Boyd | Nebraska | NE Mesonet | Complete | Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-10-10 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023-09-27 | 2023-10-30
Stuart 5NE |  | AE-21 | SAMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.6542 | -99.0843 | 643.93 | Holt | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Courtenay | Courtenay | AE-7 | CURN8 | Y | Private | Private | Existing | 47.2212 | -98.6799 | 1522 | Stutsman | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-01 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-07-15 | 2021-11-19
Ypsilanti | Ypsilanti | AE-8 | YPLN8 | N | Private | Private | New | 46.7764 | -98.5236 | 1483 | Stutsman | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-29 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-09-25 | 2023-09-30
Edgeley | Edgeley | AE-9 | EDGN8 | Y | Private | Private | Existing | 46.3192 | -98.7661 | 1649 | LaMoure | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-09-12 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-09-02 | 2022-09-28
Oakes | Oakes | AF-10 | OKNN8 | Y | University | NDSU | Existing | 46.0667 | -98.1031 | 1323 | Dickey | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | 2021-02-08 | 2021-09-02 | 2022-08-27 | 2022-01-31 | 2022-03-04 | 2021-07-29 | 2021-11-19
Columbia 8N |  | AF-11 |  | No | Federal | US FWS | New | 45.7286 | -98.2975 | 398 | Brown | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Bath 3W |  | AF-12 |  |  | Commercial | Commerical private | New | 45.4722 | -98.3785 | 1297 | Brown | South Dakota | SD Mesonet | Available | Submitted as candidate site Oct 2021; Pending Issues | Unk | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Brentford 2E | Brentford | AF-13 | BDMS2 | N | Private | Private | New | 45.1544 | -98.2781 | 397 | Spink | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2025-04-15 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-27 | 2024-11-30
Frankfurt 5W | Redfield | AF-14 | RDFS2 | N | Private | Private | New | 44.8859 | -98.4066 | 394 | Spink | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2025-04-16 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-25 | 2024-11-30
Woonsocket 4NNW | Woonsocket | AF-16 | WSMS2 |  | Private | Private | New | 44.1113 | -98.3103 | 1315 | Sandorn | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-25 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-07-21 | 2023-09-30
Mount Vernon | Mount Vernon | AF-17 | VNMS2 |  | Private | Private | New | 43.7173 | -98.2793 | 3729 | Davison | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE | Complete | 2022-08-31 | 2023-06-29 | 2022-11-15 | 2024-02-28 | 2024-02-28 | 2023-07-20 | 2023-09-30
Corsica 12W |  | AF-18 |  | No | Private | Private | New | 43.4488 | -98.6463 | 484 | Douglas | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Lake Andes 6W |  | AF-19 |  | No | Private on Tribal Lands | Yankton-Sioux Tribe; Yankton Reservation | New | 43.169 | -98.6627 | 523 | Charles Mix | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11 |  |  |  |  | Privately owned farmland w/in the Yankton Sioux Tribe/Ihanktonwan Dakota boundary - Tribal Env agency coordination required. Upland. Not in SG habitiat or undisturbed grassland.
Boyd 1 | Lynch 2W | AF-20 | LYHN1 | N | State | State Educational Lands and Funds - Leased Public | New | 42.8411 | -98.5037 | 1583 | Boyd | Nebraska | NE Mesonet | Complete | Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-09-07 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023-09-26 | 2023-10-30
O'Neill 8NNE |  | AF-21 | ONMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.5719 | -98.6005 | 601.93 | Holt | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Marion | Marion | AF-9 | MARN8 | Y | Private | Private | Existing | 46.5645 | -98.3276 | 1453 | LaMoure | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-08-25 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-08-10 | 2022-09-28
Britton 7E | Britton | AG-11 | BTMS2 | N | Private | Private | New | 45.7778 | -97.6052 | 481 | Marshall | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-05-05 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-05-29 | 2025-09-30 | Grassland Easement - SUP with USFWS
Groton | Groton | AG-12 | GOTS2 |  | Private | Private | Existing | 45.5735 | -98.0301 | 1309 | Brown | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2019-06-12 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-23
Conde 6ESE |  | AG-13 |  | No | Private | Private | New | 45.1404 | -97.9756 | 436 | Clark | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Raymond 5ENE | Clark | AG-14 | CLMS2 |  | Private | Private | New | 44.9374 | -97.8464 | 1736 | Clark | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-13 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-09-08 | 2023-09-30
Carpenter 11WSW | Carpenter | AG-15 | CPMS2 | N | Private | Private | New | 44.5732 | -98.0121 | 1298 | Beadle | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE Contractor | Complete | 2022-08-31 | 2025-05-06 | 2022-10-15 | 2025-11-15 | 2025-12-03 | 2025-07-11 | 2025-09-30
Tyndall 7NNW |  | AG-16 |  |  | Private | Private | New | 44.0933 | -97.9078 | 1321 | Sanborn | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-15 |  |  |  |  | Within Huron Wetland Management District and Sanborn County Waterfowl Production Area. Grassland and Wetland Easements.
Artesian 13N |  | AG-16 |  |  | Private | private | New | 44.1895 | -97.9713 | 1318 | Sanborn | South Dakota | SD Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Letcher 2ENE | Letcher | AG-17 | LCMS2 |  | Private | Private | New | 43.9029 | -98.1096 | 1306 | Sanborn | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE | Complete | Complete | 2022-10-12 | 2022-08-27 | 2024-02-28 | 2024-02-28 | 2022-10-21 | 2022-09-30
Parkston 2WSW |  | AG-18 | PSTS2 | Yes | Private | Private | New | 43.3808 | -98.0144 | 434 | Hutchinson | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Alexandria 6SW |  | AG-18 |  |  | Private | private | New | 43.655 | -97.8942 | 1291 | Hanson | South Dakota | SD Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned | [12 empty] | Landowner backed out - Removed
Wagner 7NNE |  | AG-19 |  | No | Private on Tribal Lands | Yankton Reservation | New | 43.1717 | -98.2442 | 1463 | Charles Mix | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-11-17
Avon 3E | Avon | AG-20 | AVMS2 | N | Private | Private | New | 43.0096 | -98.0002 | 468 | Bon Homme | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2024-10-01 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-15 | 2024-11-30
Springfield 8WNW |  | AG-20 |  |  | Private | private | New | 42.8805 | -98.0471 | 1429 | Bon Homme | South Dakota | SD Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted: removed landowners backed out; Phone convo with Nathan Edwards on 27 Nov 2023
Knox 2 | Orchard 10N | AG-21 | OHDN1 | N | State | State Educational Lands and Funds - Leased Public | New | 42.4907 | -98.2611 | 1556 | Knox | Nebraska | NE Mesonet | Complete | Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-10-11 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023-09-25 | 2023-10-30
Lake City 8E | Sica Hollow | AH-11 | SHMS2 | N | Private on Tribal Lands | Lake Traverse Reservation | New | 45.7359 | -97.2537 | 607 | Marshall | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | Tribes | Complete | Complete | 2025-05-05 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-06-04 | 2025-09-30
Erwin 5W | De Smet | AH-15 | DTMS2 |  | Private | Private | New | 44.4951 | -97.5325 | 1773 | Kingsbury | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-22 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-06-05 | 2024-09-30 | FPPA Site - Score >160; AD-1006 form submitted
Carthage 3E | Carthage | AH-16 | CGMS2 | N | Private | Private | New | 44.1673 | -97.6605 | 453 | Miner | South Dakota | SD Mesonet | Complete | Install 2024 | PY5 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete | 2024-10-03 | 2024-01-29 | 2024-12-06 | 2025-01-17 | 2024-11-18 | 2024-11-30
Salem 7NNE |  | AH-17 |  |  | Private | Private | New | 43.818 | -97.3619 | 1559 | McCook | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-15
Menno 7ESE | Menno | AH-19 | MNMS2 |  | Private | Private | New | 43.2109 | -97.4523 | 1477 | Hutchinson | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-06-05 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-06-08 | 2023-09-30
Crofton 10W |  | AH-20 | CFMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.7512 | -97.6846 | 530.66 | Knox | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Creighton 5NE |  | AH-21 | CGMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.5329 | -97.8457 | 520.1 | Knox | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
South Shore | South Shore | AI-13 | SHSS2 |  | State and Tribal Lands | South Dakota State - University Reseach Farm - Lake Traverse Reservation | Existing | 45.1055 | -97.1024 | 1850 | Codington | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2019-06-12 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-23
Clear Lake 8WSW |  | AI-14 |  |  | Private | Private | New | 44.7245 | -96.8434 | 1915 | Deuel | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-01
Kranzburg 6WSW |  | AI-14 |  |  | Private | Private | New | 44.8491 | -97.0304 | 538 | Codington | South Dakota | SD Mesonet | Removed | Install 2024 | PY4 | TO8 SD (FY23) | 2024-09-17 | 2024-11-30 | 2025-09-30 | USACE | Complete | Complete |  | 2024-01-29
Volga | Volga | AI-15 | VGAS2 |  | State | South Dakota State Univeristy | Existing | 44.3042 | -96.9189 | 1642 | Brookings | South Dakota | SD Mesonet | Complete | Resubmittal - Replacement for Gann Valley; Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | Complete | 2019-07-01 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-05-24 | 2023-09-30
Oldham 2ENE |  | AI-16 |  |  | Private | Private | New | 44.2377 | -97.2773 | 1748 | Kingsbury | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-01
Orland 5ENE | Madison | AI-17 | MDMS2 |  | Private | private | New | 43.9146 | -97.0898 | 1752 | Lake | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-13 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-05-31 | 2024-09-30
Wall Lake 7WSW | Parker | AI-18 | PKMS2 |  | Private | Private | New | 43.4885 | -97.0795 | 1469 | Turner | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-13 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-05-14 | 2024-09-30
Hurley 5SW | Hurley | AI-19 | HLMS2 |  | Private | Private | New | 43.2351 | -97.1717 | 1290 | Turner | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-25 | 2023-11-30 | 2024-12-06 | 2024-01-17 | 2024-09-24 |  | FPPA Site - Score >160; AD-1006 form submitted
Cedar 2 | Fordyce 4NW | AI-20 | FRDN1 | N | State | State Educational Lands and Funds - Leased Public | New | 42.7493 | -97.3981 | 1520 | Cedar | Nebraska | NE Mesonet | Complete | Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-09-11 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023-09-19 | 2023-10-30
Coleridge 2NNW |  | AI-21 | HNMN1 |  | Private | Private | New | 42.5268 | -97.2208 | 467.91 | Cedar | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Brookings | Brookings | AJ-15 | BKMS2 |  | State | SDSU - Univeristy Campus | Existing | 44.325 | -96.7685 | 1640 | Brookings | South Dakota | SD Mesonet | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-08 | n/a | n/a | USACE Contractor | Complete | Complete | 2019-06-13 | 2022-08-27 | 2020-09-22 | 2021-01-30 | 2018-07-25 | 2021-11-19
Flandreau | Flandreau | AJ-16 | FLNS2 |  | Private | Private | Existing | 44.0867 | -96.5849 | 1624 | Moody | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 8/31/2022 (Orig. Sampling in 2019) | n/a | 2024-02-28 | 2024-02-28 | 2022-07-29 | 2022-08-20
Sioux Falls | Sioux Falls | AJ-18 | SFSS2 |  | Private | Private | Existing | 43.5048 | -96.7623 | 1407 | Minnehaha | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 6/14/2022 (Orig. Sampling in 2019) | n/a | 2024-02-28 | 2024-02-28 | 2022-07-13 | 2022-08-20
Beresford | Beresford | AJ-19 | BFMS2 |  | State | South Dakota State Univeristy | Existing - Moved > 100ft | 43.0404 | -96.9011 | 1278 | Clay | South Dakota | SD Mesonet | Complete | Install 2021; Sub for Martin on T01 | PY1 | TO1 SD (FY20) Mod | 2021-12-03 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-04-13 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-12-09 | 2021-12-23
Martinsburg 5WNW |  | AJ-21 | MNMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.5369 | -96.9171 | 457.25 | Dixon | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Buffalo Lake E | Buffalo Lake E | B-01 | BUFM8 |  | Tribal Lands | Blackfeet Indian Reservation | New | 48.8536 | -112.6562 | 4121 | Glacier | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-10-16 | 2024-09-30
Mission Lake S | Mission Lake S | B-02 | MINM8 |  | Tribal Lands | Blackfeet Indian Reservation | New | 48.5273 | -112.6334 | 4147 | Glacier | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-10-14 | 2024-09-30
Dupuyer N | Dupuyer N | B-03 | DYRM8 |  | Private | Private | New | 48.2956 | -112.5492 | 3890 | Pondera | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-27 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-06-22 | 2023-09-30
Bynum W | Bynum W | B-04 | BYUM8 |  | Private | Private | New | 47.9572 | -112.4944 | 4439 | Teton | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-28 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-06-21 | 2023-09-30
Augusta N | Augusta N | B-05 | AGNM8 | N | Private | Private | New | 47.5853 | -112.36 | 4321 | Teton | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-08 | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Bowmans Corner NW | Bowmans Corner NW | B-06 | BNWM8 |  | Private | Private | New | 47.308 | -112.1728 | 4267 | Lewis & Clark | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) MOD | 2023-09-13 | 2023-11-30 | 2024-11-30 | USACE Contractor | Aug 2022 | 2022-08-31 | Denied | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-10-22 | 2023-09-30 | FPPA >160
Canyon Creek |  | B-07 |  |  | Private | Private | New | 46.8014 | -112.1941 | 4265 | Lewis & Clark | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Whitehall N |  | B-10 |  |  | Private | Private | New | 45.9015 | -112.1401 | 4674 | Jefferson | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Laurin |  | B-11 |  |  | NGO | Ranch Resources | New | 45.3621 | -112.1333 | 5030 | Madison | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Sunburst NW | Sunburst NW | C-01 | SBSM8 |  | Private | Private | New | 48.915 | -112.0222 | 3743 | Toole | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO5 (FY23) | 2024-09-16 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2025-06-04 | 2022-09-15 | 2025-01-10 | 2025-02-05 | 2024-07-19 | 2024-10-20 | FPPA >160
Ethridge N | Ethridge N | C-02 | ETNM8 | N | Private | Private | New | 48.6111 | -112.1457 | 3498 | Toole | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-04 | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Conrad N | Conrad N | C-03 | CNNM8 |  | Private | Private | New | 48.3045 | -111.9243 | 3704 | Pondera | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-01 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-07 | 2024-09-30 | FPPA >160
Midway Colony | Midway Colony | C-04 | RADM8 |  | Private | Private | New | 48.061 | -112.0077 | 3778 | Pondera | Montana | MT Climate Office | Complete | Replacement for Conrad ARC on TO2 | PY2 | TO2 MT (FY21) MOD | 2022-07-12 | 2022-10-30 | 2023-10-30 | USACE Contractor | Complete | Complete | 2022-05-18 | n/a | 2022-12-12 | 2023-08-25 | 2022-10-24 | 2022-11-01
Fairfield | Fairfield | C-05 | FARM8 | N | Private | Private | New | 47.6846 | -111.9394 | 3906 | Teton | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-23 | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Sun River SE | Sun River SE | C-06 | SURM8 |  | Private | Private | New | 47.4118 | -111.7173 | 3596 | Cascade | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-09-27 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-11 | 2023-09-30
Craig |  | C-07 |  |  | Private | Private | New | 47.0881 | -111.9829 | 3682 | Lewis & Clark | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-03
E Helena |  | C-08 |  |  | Private | Private | New | 46.5883 | -111.8614 | 4606 | Lewis & Clark | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Elkhorn Creek |  | C-09 |  |  | Private | Private | New | 46.2015 | -111.9649 | 5103 | Jefferson | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-03
MDA Toston | Toston | C-10 | TTNM8 |  | Private | Private | Existing | 46.1365 | -111.5432 | 4067 | Broadwater | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-19 | n/a | 2022-12-12 | 2023-08-25 | 2022-09-21 | 2022-09-22
Red Bluff |  | C-11 |  |  | State | MT State University | New | 45.5776 | -111.6524 | 4869 | Madison | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Canyon Ferry N |  | C-8 | CFDM8 |  | Federal | USFS | New | 46.6473 | -111.6222 | 4262 | Broadwater | Montana | MT Climate Office | Removed | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 |  |  |  |  | To steep to install
MDA Oilmont | MDA Oilmont | D-01 | OILM8 |  | Private | Private | Existing | 48.7816 | -111.6011 | 3597 | Toole | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-05-17 | n/a | 2022-12-12 | 2023-08-25 | 2022-09-16 | 2022-09-22
Crooked Coulee |  | D-02 |  |  | Private | Private | New | 48.5449 | -111.5614 | 3204 | Toole | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Bootlegger S CG SW | Bootlegger S CG SW | D-03 | LEGM8 | N | Private | Private | New | 48.3147 | -111.3428 | 3228 | Toole | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-18 | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Brady NE | Brady NE | D-04 | BRYM8 |  | Private | Private | New | 48.1032 | -111.6643 | 3376 | Pondera | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-29 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-06-27 | 2023-09-30
Benton Lake W | Benton Lake W | D-05 | BLWM8 |  | Private | Private | Existing | 47.6907 | -111.4736 | 3706 | Cascade | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-09-08 | n/a | 2022-12-12 | 2023-08-25 | 2022-10-21 | 2022-11-01
Eden NW | Eden NW | D-06 | ENWM8 | N | Private | Private | New | 47.316 | -111.3333 | 4084 | Cascade | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-05-18 | 2026-01-09 |  |  | 2025-09-30
Milligan |  | D-07 | MLEM8 |  | Private | Private | New | 47.0099 | -111.3341 | 4709 | Cascade | Montana | MT Climate Office | Candidate | Location Change; Redoing cultural & env | PY7 | TO9 MT (FY25) | [7 empty] | 5/18/2024; 7/16/2025
Rader Elk Creek | Rader | D-08 |  |  | Private | Private | New | 46.6569 | -111.2382 | 5105 | Meagher | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Canton |  | D-09 |  |  | Private | Private | New | 46.4203 | -111.4227 | 4147 | Broadwater | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Morgan Cemetery |  | D-10 |  |  | Private | Private | New | 46.0327 | -111.1321 | 5270 | Gallatin | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Bozeman | Bozeman | D-11 | BZNM8 |  | State | Montana State University | Existing | 45.6621 | -111.0463 | 4927 | Gallatin | Montana | MT Climate Office | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-09 | n/a | n/a | USACE Contractor | Complete | Complete | 2021-09-10 | Y | n/a | n/a | 2020-10-30 | 2021-11-19
Mt Lebanon SE | Mt Lebanon SE | E-01 | MTLM8 |  | Private | Private | New | 48.8523 | -111.0375 | 4121 | Liberty | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-15 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-16 | 2024-09-30 | FPPA >160
Chester N |  | E-02 |  |  | Private | Private | New | 48.69 | -110.9832 | 3396 | Liberty | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Hill S |  | E-02 |  |  | Private | Private | New | 48.6887 | -111.1279 | 3606 | Liberty | Montana | MT Climate Office | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) REMOVED | [12 empty] | FPPA >160 - Land owner pulled out of location
Chester SW | Chester SW | E-03 | CHSM8 |  | Private | Private | New | 48.4477 | -111.0376 | 3103 | Liberty | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-30 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-06-28 | 2023-09-30
Carter N | Carter N | E-04 | CRNM8 |  | Private | Private | New | 48.0223 | -110.993 | 3492 | Choteau | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-10 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-07-15 | 2024-09-30 | FPPA >160
Highwood Bench | Highwood Bench | E-05 | HIWM8 |  | Private | Private | New | 47.6848 | -110.8996 | 3329 | Choteau | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO5 (FY23) | 2024-09-16 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2025-08-28 | 2023-10-12 | 2025-01-10 | 2025-02-05 | 2024-07-12 | 2024-10-20
Belt NW | Belt NW | E-06 | ELTM8 | N | Private | Private | New | 47.4276 | -111.0177 | 3781 | Cascade | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-26 | 2024-05-18 | 2026-01-09 |  |  | 2025-09-30
S Fork Smith |  | E-09 |  |  | Private | Private | New | 46.4438 | -110.9394 | 5123 | Meagher | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Fox Crossing SW | Fox Crossing SW | F-01 | FOXM8 |  | Private | Private | New | 48.8994 | -110.7485 | 3136 | Hill | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-12 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-03 | 2024-09-30 | FPPA >160
Inverness N | Inverness N | F-02 | INNM8 |  | Private | Private | New | 48.7189 | -110.7097 | 3208 | Hill | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-12 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-06 | 2024-09-30 | FPPA >160
Inverness S | Inverness S | F-03 | ISSM8 |  | Private | Private | New | 48.3754 | -110.7126 | 3065 | Hill | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-13 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-07-18 | 2024-09-30
Loma | Loma N | F-04 | LOAM8 |  | Private | Private | New | 47.9537 | -110.4917 | 2768 | Choteau | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO5 (FY23) | 2024-09-16 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2025-05-28 | 2023-10-04 | 2025-01-10 | 2025-02-05 | 2024-07-12 | 2024-10-20
Frenchman Ridge | Frenchman Ridge | F-05 | RIGM8 | N | Private | Private | New | 47.7482 | -110.5505 | 3537 | Choteau | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-28 | 2024-05-18 | 2026-01-09 |  |  | 2025-09-30
Knerrville |  | F-06 |  |  | Private | Private | New | 47.3864 | -110.436 | 4606 | Judith Basin | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Surprise Creek |  | F-07 |  |  | Private | Private | New | 47.1682 | -110.3264 | 4378 | Judith Basin | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Twodot E | Twodot E | F-09 | TWOM8 |  | Private | Private | New | 46.4468 | -110.2055 | 4643 | Wheatland | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-13 | 2023-09-30
Springdale | Springdale | F-11 | SDLM8 |  | Private | Private | New | 45.7465 | -110.1568 | 4294 | Sweet Grass | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO5 (FY23) | 2024-09-16 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2025 | 2023-10-12 | 2025-01-10 | 2025-02-05 | 2024-05-18 | 2024-10-20 | Submitted as new location for Springdale N
Simpson | Simpson | G-01 | SMPM8 | N | Private | Private | New | 48.9283 | -110.1941 | 2781 | Hill | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-05-29 | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Kremlin NW | Kremlin NW | G-02 | KLNM8 | N | Private | Private | New | 48.7389 | -110.2174 | 2755 | Hill | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-21 | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Big Sandy NW | Big Sandy NW | G-03 | BSWM8 |  | Private | Private | New | 48.2416 | -110.3217 | 2858 | Choteau | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-11 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-07-17 | 2024-09-30 | FPPA <160
Big Sandy SE | Big Sandy SE | G-04 | BSEM8 |  | Private | Private | New | 48.034 | -110.0359 | 3099 | Choteau | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-11 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-10 | 2024-09-30 | FPPA >160
Graceville |  | G-05 |  |  | Private | Private | New | 47.7143 | -110.0404 | 3194 | Choteau | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Coffee Creek N | Coffee Creek N | G-06 | CFCM8 |  | Private | Private | Existing | 47.3935 | -110.1083 | 3739 | Fergus | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-09-07 | n/a | 2022-12-12 | 2023-08-25 | 2022-09-19 | 2022-09-22
Moccasin ARC | Moccasin | G-07 | MCIM8 |  | University | Agriculture Research Center - Montana State University | Existing | 47.0585 | -109.9535 | 4257 | Judith Basin | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-09-01 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-05-13 | 2021-11-19
Judith Gap | Judith Gap | G-08 | JGPM8 |  | Private | Private | New | 46.7189 | -109.7684 | 4646 | Judith Basin | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-05-29 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-07-11 | 2024-09-30
Harlowton E | Harlowton E | G-09 | HWTM8 |  | Private | Private | New | 46.413 | -109.7009 | 4086 | Wheatland | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-13 | 2023-09-30
Melville SE | Melville | G-10 | MLVM8 |  | Private | Private | Existing | 46.0015 | -109.8416 | 4710 | Sweet Grass | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-17 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-09-12 | 2021-11-19
Big Timber SE | Big Timber SE | G-11 | BTSM8 |  | Private | Private | Existing | 45.7435 | -109.8267 | 4423 | Sweet Grass | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-20 | n/a | 2022-12-12 | 2023-08-25 | 2022-08-23 | 2022-09-01
Absarokee W | Absarokee | G-12 | KEEM8 |  | Private | Private | Existing | 45.5573 | -109.6112 | 4608 | Stillwater | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-03 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-06-02 | 2021-11-19
Lake Thibadeau W | Lake Thibadeau W | H-02 | LTBM8 |  | Private | Private | New | 48.746 | -109.6417 | 2627 | Hill | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-26 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-17 | 2024-09-30 | FPPA >160
Havre ARC | Havre | H-03 | HAEM8 |  | University | Agriculture Research Center - Montana State University | Existing | 48.4891 | -109.7994 | 2721 | Hill | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-05-19 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-05-12 | 2021-11-19
Warrick S | Warrick S | H-04 | RICM8 | N | Private | Private | New | 47.9893 | -109.6392 | 3532 | Hill | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Judith Landing |  | H-05 |  |  | Private | Private | New | 47.7575 | -109.6738 | 3205 | Choteau | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Christina W | Christina W | H-06 | CSTM8 |  | Private | Private | New | 47.4245 | -109.5207 | 3606 | Fergus | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-05-30 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-07-11 | 2024-09-30
Beaver Creek |  | H-08 |  |  | Private | Private | New | 46.8728 | -109.4617 | 5446 | Fergus | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Rothiemay W | Rothiemay W | H-09 | RMYM8 |  | Private | Private | New | 46.5351 | -109.3477 | 4364 | Golden Valley | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-05-08 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-18 | 2023-09-30
Ryegate S | Ryegate S | H-10 | RGTM8 |  | Private | Private | New | 46.1995 | -109.3111 | 4272 | Golden Valley | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-05-10 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-19 | 2023-09-30
Rapelje 2 | Rapelje 2 | H-11 | RAPM8 |  | Private | Private | New | 45.8607 | -109.4495 | 4710 | Stillwater | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-20 | 2023-09-30
Cooney Reservoir NW | Cooney Reservoir NW | H-12 | COOM8 |  | Private | Private | Existing | 45.4658 | -109.2597 | 4702 | Stillwater | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-21 | n/a | 2022-12-12 | 2023-08-25 | 2022-08-20 | 2022-09-01
Red Lodge |  | H-13 |  |  | Private | Private | New | 45.2223 | -109.2638 | 5498 | Carbon | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Ralston 14WNW |  | H-14 |  |  | Private | Private | New | 44.8841 | -109.1071 | 4314 | Park | Wyoming | Wyoming Mesonet | Candidate | Install 2026 | PY6 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2024-09-05
Chinook N |  | I-02 |  |  | Private | Private | New | 48.7358 | -109.1481 | 2803 | Blaine | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Cleveland N | Cleveland N | I-03 | EVEM8 | N | Private | Private | New | 48.3868 | -109.1378 | 3065 | Blaine | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-10 | 2023-11-02 | 2026-01-09 |  |  | 2025-09-30
Rattlesnake |  | I-04 |  |  | Private | Private | New | 48.0921 | -109.075 | 3404 | Blaine | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Winifred NE | Woodhawk | I-05 | WNFM8 |  | Private | Private | New | 47.7319 | -109.2019 | 3220 | Fergus | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-05-28 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-10-19 | 2024-09-30
Forestgrove N | Forestgrove N | I-07 | FRGM8 |  | Private | Private | New | 47.1058 | -109.0888 | 4103 | Fergus | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-09-28 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-14 | 2023-09-30
Elk Creek Tyler | Elk Creek | I-08 |  |  | Private | Private | New | 46.8787 | -108.8616 | 4523 | Fergus | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Lavina N | Lavina N | I-09 | LVAM8 |  | Private | Private | New | 46.3989 | -108.9536 | 3684 | Golden Valley | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-05-09 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-19 | 2023-09-30
Broadview E | Broadview E | I-10 | BDVM8 |  | Private | Private | Existing | 46.1282 | -108.7554 | 4095 | Yellowstone | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-17 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-08-14 | 2021-11-19
Molt S | Molt S | I-11 | MOTM8 |  | Private | Private | New | 45.8414 | -108.9592 | 3899 | Stillwater | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-02 | 2023-09-30
Silesia |  | I-12 |  |  | Private | Private | New | 45.5666 | -108.8495 | 3531 | Carbon | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Bridger |  | I-13 |  |  | County | MT Conservation Districts | New | 45.2665 | -108.8794 | 3764 | Carbon | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Powell | Powell | I-14 | PLMW4 |  | Univeristy | UWY | New | 44.7764 | -108.759 | 4372 | Park | Wyoming | Wyoming Mesonet | Complete | Install 2021 | PY1 | TO1 WY (FY20) | 2020-09-28 | 2021-09-30 | 2022-09-30 | USACE Staff | Complete | Complete | 2022-08-03 | 2022-02-24 | 2022-02-24 | 2022-03-29 | 2021-12-17 | 2021-12-18
Wapiti 6E | Buffalo Bill Reservoir | I-15 | BBMW4 |  | Federal | BOR | New | 44.4817 | -109.3083 | 5433 | Park | Wyoming | Wyoming Mesonet | Complete | MOD on TO1 award; Install 2022 | PY2 | TO1 WY (FY20) MOD | 2022-08-15 | 2022-12-30 | 2023-12-30 | USACE Staff | Complete | 1/7/2022 | 2022-08-17 | na | 2023-10-30 | 2023-10-30 | 2022-09-15 | 2022-12-22
Pavillion 13W | Diversion Dam | I-19 | DDMW4 |  | Federal | BOR | New | 43.2314 | -108.9515 | 5682 | Fremont | Wyoming | Wyoming Mesonet | Complete | Install 2022 | PY2 | TO2 WY (FY21) MOD | 2022-09-21 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2021-08-30 | 2022-10-19 | 2022-08-27 | 2023-10-30 | 2023-10-30 | 2022-09-29 | 2022-09-30
Fort_Washakie |  | I-20 | FWMW4 |  | Tribal Lands | Wind River Reservation | New | 43.005 | -108.8803 | 5571 | Fremont | Wyoming | Wyoming Mesonet | In-Progress | 106 and NEPA complete. Waiting on RE. | PY2 | TO1 WY (FY20) MOD | 2022-08-15 | 2022-12-30 | 2023-12-30 | USACE Staff | Complete | 2022-01-20 | Push to 2024 | na
Hogeland SW | Hogeland SW | J-02 | HOGM8 |  | Private | Private | New | 48.8163 | -108.7802 | 3334 | Blaine | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-14 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-19 | 2024-09-30
Savoy SW | Savoy SW | J-03 | SVYM8 |  | Tribal Lands | Fort Belknap Tribes - Reservation | New | 48.417 | -108.5907 | 2459 | Blaine | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO5 (FY23) | 2024-09-16 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2025 | 2023-11-02 | 2025-01-10 | 2025-02-05 | 2024-10-18 | 2024-10-20 | Replacement for Ft. Belknap and Hayes sites from 2023 on Ft. Belknap Tribes
Dry Lake | Dry Lake | J-04 | DRYM8 |  | Tribal Lands | Fort Belknap Tribes - Reservation | New | 48.0419 | -108.6416 | 3418 | Blaine | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO5 (FY23) | 2024-09-16 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2025 | 2023-11-02 | 2025-01-10 | 2025-02-05 | 2024-10-17 | 2024-10-20 | Replacement for Ft. Belknap and Hayes sites from 2023 on Ft. Belknap Tribes
DY Junction |  | J-05 |  |  | NGO | American Prairie Foundation | New | 47.7243 | -108.6995 | 2958 | Phillips | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Roy E | Roy E | J-06 | RYOM8 |  | Private | Private | New | 47.3791 | -108.6778 | 3038 | Fergus | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-22 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-03 | 2023-09-30
War Horse NW | War Horse NW | J-07 | WRHM8 |  | Private | Private | New | 47.1472 | -108.5913 | 3151 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-23 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-13 | 2023-09-30
Winnett SW | Winnett SW | J-08 | WIEM8 |  | Private | Private | New | 46.9654 | -108.5024 | 3202 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-24 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-25 | 2023-09-30
Roundup NE | Roundup | J-09 | ROUM8 |  | Private | Private | Existing | 46.5785 | -108.4243 | 3448 | Musselshell | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-06-08 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-06-09 | 2021-11-19
Huntley ARC | Huntley E | J-11 | HNTM8 |  | University | Agriculture Research Center - Montana State University | Existing | 45.9264 | -108.233 | 3055 | Yellowstone | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-06-03 | n/a | 2022-12-12 | 2023-08-25 | 2022-09-29 | 2022-11-01
Billings S | Billings S | J-12 | BNGM8 |  | Private | Private | New | 45.6259 | -108.4906 | 4039 | Yellowstone | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-04-25 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-07-11 | 2024-09-30 | FPPA >160
Cowley 4NNE | Cowley | J-14 | CYMW4 |  | Federal | BOR | New | 44.9291 | -108.4324 | 4121 | Big Horn | Wyoming | Wyoming Mesonet | Complete | Install 2022 | PY2 | TO2 WY (FY21) MOD | 2022-09-21 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 8/30/2021 | 2022-10-12 | na | 2023-10-30 | 2023-10-30 | 2022-09-29 | 2022-09-30
Otto 7NNE (formerly Emblem N) |  | J-15 |  |  | Federal | BLM - Cody FO | New | 44.4993 | -108.2256 | 4141 | Bighorn | Wyoming | Wyoming Mesonet | Candidate | Install 2027 | PY7 | TO 10 WY(FY25) |  |  |  | USACE |  |  |  | 2024-09-02
Burlington 5SSE (formerly Otto SE) |  | J-16 |  |  | Federal | BLM - Worland FO | New | 44.376 | -108.406 | 4443 | Big Horn | Wyoming | Wyoming Mesonet | Candidate | Install 2027 | PY7 | TO 10 WY(FY25) |  |  |  | USACE |  |  |  | 2024-09-03
Kirby 6N (NOT FINALIZED LOCATION) |  | J-17 |  |  | Private | Private | New | 43.8872 | -108.1905 | 4357 | Washakie | Wyoming | Wyoming Mesonet | Removed | Install 2027 | PY7 | TO 10 WY(FY25) |  |  |  | USACE |  |  |  | 2024-09-06
Thermopolis |  | J-18 |  |  | Private | Private | New | 43.6613 | -108.234 | 4838 | Hot Springs | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY (FY26) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-09-09
Shoshoni 6NNW | Boysen Reservoir | J-19 | BYMW4 |  | Federal | BOR | New | 43.3239 | -108.1331 | 4761 | Fremont | Wyoming | Wyoming Mesonet | Complete | Install 2022 | PY2 | TO2 WY (FY21) | 2022-09-21 | 2022-09-30 | 2023-09-30 | USACE Staff | Complete | 8/30/2021 | 2022-09-21 | na | 2023-10-30 | 2023-10-30 | 2022-09-29 | 2022-09-30
Saint Stephens 7SSW(formerly Riverton SE) |  | J-20 |  |  | Federal | BLM - Lander FO | New | 42.8676 | -108.2667 | 5309 | Fremont | Wyoming | Wyoming Mesonet | Candidate | Install 2027 | PY7 | TO 10 WY(FY25) |  |  |  | USACE |  |  |  | 2024-09-04
Fort Belknap S |  | J-3 |  |  | Tribal Lands | Fort Belknap Tribes | New | 48.4535 | -108.7704 | 2470 | Blaine | Montana | MT Climate Office | Removed | Submitted as candidate site Oct 2021 - Fort Belkap THPO Cleared | PY4 | Unk. Timeline - Re -siting |  |  |  | Tribe | Complete | [7 empty] | Getting resited
Hays N |  | J-4 |  |  | Tribal Lands | Fort Belknap Tribes | New | 48.1978 | -108.7055 | 2967 | Blaine | Montana | MT Climate Office | Removed | Submitted as candidate site Oct 2021 - Fort Belkap THPO Cleared | PY4 | Unk. Timeline |  |  |  | Tribe | Complete | [7 empty] | Getting resited
Turner N | Turner N | K-02 | TRNM8 |  | Private | Private | New | 48.8743 | -108.3937 | 3073 | Blaine | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-02 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-09-11 | 2023-09-30
Dodson N |  | K-03 |  |  | Private | Private | New | 48.5628 | -108.2078 | 2840 | Phillips | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Wagner SW (formerly Dodson) | Wagner S | K-04 | WAGM8 | N | Private | Private | New | 48.2629 | -108.1489 | 2560 | Phillips | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-04 | 2026-01-09 |  |  | 2025-09-30
Matador Ranch | Matador Ranch | K-05 | MTRM8 |  | Non-Profit | The Nature Conservancy | New | 47.9264 | -108.3359 | 3027 | Phillips | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-04 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-09-08 | 2023-09-30
Valentine E | Dovetail | K-06 | VLTM8 |  | Private | Private | New | 47.358 | -108.2438 | 2904 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-22 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-04 | 2023-09-30
Jitney Road (Mosby NW) | Jitney Road | K-07 | MOBM8 |  | Private | Private | New | 47.0611 | -108.098 | 2989 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-21 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-26 | 2023-09-30
Mosby S | Mosby S | K-08 | MOYM8 |  | Private | Private | New | 46.7823 | -107.9213 | 2805 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-10-16 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-12 | 2023-09-30
Musselshell | Musselshell | K-09 | MSSM8 |  | Private | Private | New | 46.54 | -108.0218 | 3132 | Musselshell | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-10-20 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-11 | 2023-09-30
Fly Creek |  | K-11 |  |  | Private | Private | New | 45.9169 | -107.9702 | 3037 | Yellowstone | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-24
Shell 6W |  | K-15 |  |  | Private | Private | New | 44.5207 | -107.9112 | 4057 | Big Horn | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY (FY26) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-09-07
Manderson 4E |  | K-16 |  |  | Private | Private | New | 44.2588 | -107.8752 | 4002 | Big Horn | Wyoming | Wyoming Mesonet | Candidate | Install 2026 | PY6 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2024-09-08
Worland 3E | Worland 3E | K-17 | WRMW4 |  | Federal | BOR | New | 44.0026 | -107.905 | 4203 | Washakie | Wyoming | Wyoming Mesonet | Complete | MOD on TO1 award; Install 2022 | PY2 | TO1 WY (FY20) MOD | 2022-08-15 | 2022-12-30 | 2023-12-30 | USACE Staff | Complete | 2022-01-07 | 2022-08-24 | na | 2023-10-30 | 2023-10-30 | 2022-09-22 | 2022-12-22
Thermopolis 17E |  | K-18 |  |  | Private | Private | New | 43.6287 | -107.8648 | 5050 | Hot Springs | Wyoming | Wyoming Mesonet | Candidate | Install 2026 | PY6 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2024-09-10
Lysite 5N |  | K-19 |  |  | Private | Private | New | 43.3161 | -107.6927 | 5328 | Fremont | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY(FY25) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-09-11
Loring SW | Loring SW | L-02 | LORM8 |  | Private | Private | New | 48.7716 | -107.8779 | 2821 | Phillips | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-01 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-09-07 | 2023-09-30
Lake Bowdoin NW |  | L-03 |  |  | Private | Private | New | 48.4385 | -107.7512 | 2418 | Phillips | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Content | Content | L-04 | TNTM8 | N | Private | Private | New | 48.0177 | -107.5792 | 2320 | Philllips | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-19 | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Sun Prairie | Sun Prairie | L-05 | SNPM8 | N | NGO | American Prairie Foundation | New | 47.7689 | -107.6761 | 2702 | Phillips | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Brusett NW | Brusett NW | L-06 | USEM8 | N | Private | Private | New | 47.522 | -107.5156 | 3306 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Sand Springs NW | Sand Springs NW | L-07 | SDSM8 |  | Private | Private | New | 47.1653 | -107.6384 | 3007 | Garfield | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-25 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-07-27 | 2023-09-30
Mosby SE | Mosby SE | L-08 | MBYM8 |  | Private | Private | New | 46.9362 | -107.6511 | 3176 | Garfield | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-04-05 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-08 | 2024-09-30
Tullock School |  | L-10 |  |  | Private | Private | New | 46.0681 | -107.4 | 2886 | Treasure | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-08-29
Kingley E |  | L-11 |  |  | Private | Private | New | 45.9449 | -107.5253 | 3044 | Big Horn | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-03
Crow Agency E | Crow Agency | L-12 | CROM8 |  | Tribal Lands | Crow indian reservation | Existing | 45.5861 | -107.4383 | 3119 | Big Horn | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-08 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-09-04 | 2021-11-19
Lodge Grass W | Lodge Grass W | L-13 | LGGM8 |  | Private on Tribal Lands | Crow indian reservation | New | 45.3073 | -107.5154 | 3824 | Big Horn | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-18 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-25 | 2023-09-30
Dayton |  | L-14 |  |  | Private | Private | New | 44.9237 | -107.2714 | 4101 | Sheridan | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY(FY26) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE |  |  |  | 2024-09-17
Ten Sleep |  | L-17 |  |  | Federal | BLM - Worland FO | New | 44.0204 | -107.4309 | 4702 | Washakie | Wyoming | Wyoming Mesonet | Candidate | Install 2027 | PY7 | TO 10 WY(FY25) |  |  |  | USACE |  |  |  | 2024-09-01
Turkey Track |  | M-02 |  |  | Federal | DOI/BLM | New | 48.7977 | -107.3464 | 2777 | Phillips | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Bjornberg |  | M-03 |  |  | Federal | DOI/BLM | New | 48.4913 | -107.2088 | 2213 | Valley | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-07-16
Saco S | Saco S | M-04 | SASM8 |  | Private | Private | New | 48.2908 | -107.3912 | 2741 | Phillips | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-03 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-09-09 | 2023-09-30
Barth Spring | Barth Spring | M-05 | ARTM8 | N | Private | Private | New | 47.8242 | -107.2374 | 2913 | Valley | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Sage Hen Buttes | Sage Hen Buttes | M-06 | SGHM8 | N | Private | Private | New | 47.4544 | -106.9797 | 2869 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-05-18 | 2026-01-09 |  |  | 2025-09-30
Brusett E |  | M-06 |  |  | Private | Private | New | 47.4376 | -107.1188 | 2944 | Garfield | Montana | MT Climate Office | Removed | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Edwards E | Edwards E | M-07 | EDEM8 | N | Private | Private | New | 47.178 | -107.1767 | 2872 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Fig Mountain (Formerly Blazier Butte) | Fig Mountain | M-08 | BLZM8 | N | Private | Private | New | 47.0098 | -107.0051 | 3259 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Ingomar NE | Ingomar NE | M-09 | IGMM8 |  | Private | Private | Existing | 46.6568 | -107.2238 | 3098 | Rosebud | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-04 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-08-12 | 2021-11-19
Sanders N | Ingomar | M-10 | SDRM8 | N | Private | Private | New | 46.3164 | -107.0799 | 2597 | Treasure | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO7 MT (FY25) | 2025-04-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-07-25 | 2026-01-09 |  |  | 2025-09-30
Sarpy Creek | Forsyth S | M-11 | SPYM8 | N | Private | Private | New | 45.9633 | -107.0853 | 3316 | Treasure | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO7 MT (FY25) | 2025-04-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-07-25 | 2026-01-09 |  |  | 2025-09-30
Busby S | Busby S | M-12 | BUSM8 |  | Private on Tribal Lands | Northern Cheyenne Indian Reservation | New | 45.5186 | -106.9316 | 3582 | Big Horn | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-17 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-26 | 2023-09-30
Youngs Creek |  | M-13 |  |  | Private on Tribal Lands | Crow Reservation | New | 45.1798 | -107.1304 | 4942 | Big Horn | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-03
Sheridan | Sheridan | M-14 | SHMW4 |  | Univeristy | UWY | New | 44.8407 | -106.839 | 3738 | Sheridan | Wyoming | Wyoming Mesonet | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-10 |  |  | USACE Contractor | Complete | Complete | 2022-07-28 | Y | Y | Y | 2020-10-15 | 2020-10-16
Little Fork |  | M15 |  |  | Private | Private | New | 44.4898 | -106.5722 | 4836 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2022-10-31
Shorma-Meade Creek | Banner 7N | M-15 | BAMW4 | N | Private | Private | New | 44.704 | -106.8614 | 4158 | Sheridan | Wyoming | Wyoming Mesonet | Complete | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24) | 2024-09-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-12 | 2023-12-20 |  |  |  | 2025-09-30
Thoeny N |  | N-02 |  |  | Private | Private | New | 48.9577 | -106.9201 | 2564 | Valley | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Tampico N | Tampico N | N-03 | TAMM8 |  | Private | Private | New | 48.3646 | -106.8509 | 2158 | Valley | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-26 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-23 | 2024-09-30
Glasgow SW | Glasgow SW | N-04 | GLOM8 |  | Private | Private | New | 48.1244 | -106.7489 | 2272 | Valley | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-24 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-22 | 2024-09-30
The Pines | The Pines | N-05 | PNEM8 | N | Federal | USACE | New | 47.8549 | -106.6674 | 2410 | Valley | Montana | MT Climate Office | Complete | Submitted as Candidate Fall 2023 - Proposed for 2nd TO Fy23 - Install 2024 | PY5 | TO7 MT (FY25) | 2025-04-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Kester School S | Kester School S | N-06 | KSSM8 | N | Private | Private | New | 47.5584 | -106.6641 | 2599 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Cohagen N | Cohagen N | N-07 | OHNM8 | N | Private | Private | New | 47.1207 | -106.6444 | 2903 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Cohagen S | Cohagen S | N-08 | HAGM8 | N | Private | Private | New | 46.9123 | -106.6809 | 2982 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Forsyth S | Sarpy Creek | N-10 | FSSM8 | N | Private | Private | New | 46.1797 | -106.707 | 2853 | Rosebud | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO7 MT (FY25) | 2025-04-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-07-25 | 2026-01-09 |  |  | 2025-09-30
Hay Coulee |  | N-11 |  |  | Private | Private | New | 45.8098 | -106.5213 | 3037 | Rosebud | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-24
Lame Deer E | Lame Deer E | N-12 | LMDM8 |  | Tribal Lands | Northern Cheyenne Indian Reservation | New | 45.656 | -106.4879 | 4265 | Rosebud | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | Tribe | Aug 2022 | 2022-08-31 | 2023-07-19 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-29 | 2023-09-30
Birney | Birney | N-13 | BYSM8 | N | Private | Private | New | 45.3384 | -106.5167 | 3194 | Rosebud | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO7 MT (FY25) | 2025-04-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-05-18 | 2026-01-09 |  |  | 2025-09-30
SR Cattle | Wyarno 6E | N-14 | WYMW4 | N | Private | Private | New | 44.9076 | -106.6008 | 3823 | Sheridan | Wyoming | Wyoming Mesonet | Complete | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO7 WY (FY25) | 2025-04-21 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-22 | 2023-12-20
Watt |  | N15 |  |  | Private | Private | New | 44.4846 | -106.8214 | 4502 | Johnson | Wyoming | Wyoming Mesonet | Removed | Install 2024 | PY4 | TO4 WY (FY23) |  |  |  |  | Complete | Complete |  | 2022-10-31 |  |  |  |  | ENV - Burrowing Owl, burrowing owl - do survey in June and if you see anything delay construction until Sept 16th OR don't do survey and delay construction. ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Banner 11ESE (Formerly Morey) |  | N-15 |  |  | Private | Private | New | 44.5512 | -106.6144 | 4233 | Johnson | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY (FY26) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-30
Tipperary |  | N16 |  |  | Private | Private | New | 44.4079 | -106.3951 | 4098 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2022-10-31
Camino 2 | Buffalo 8S | N-16 | BUMW4 | N | Private | Private | New | 44.2353 | -106.6878 |  | Johnson | Wyoming | Wyoming Mesonet | Complete | Install 2025 | PY5 | TO6 WY (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-10 | 2023-12-20 |  |  |  | 2025-09-30
Camino | Kaycee 23NNE | N-17 | CMMW4 |  | Private | Private | New | 44.0091 | -106.4436 | 4806 | Johnson | Wyoming | Wyoming Mesonet | Complete | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete | 2024-08-21 | 2023-01-12 | 2025-01-22 | 2025-05-15 | 2024-08-31 | 2024-09-30 | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Schiffer | Kaycee 9SE | N-18 | KCMW4 | N | Private | Private | New | 43.6063 | -106.5404 | 4806 | Johnson | Wyoming | Wyoming Mesonet | Complete | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO7 WY (FY25) | 2025-04-21 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-17 | 2023-10-12 |  |  |  | 2025-09-30
Dead Horse Ranch - Shepperson | Midwest 12WSW | N-19 | MWMW4 | N | Private | Private | New | 43.3666 | -106.5106 | 5205 | Natrona | Wyoming | Wyoming Mesonet | Complete | Install 2025 | PY5 | TO6 WY (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-01 | 2023-10-12
Ophiem S | Ophiem S | O-02 | OHMM8 |  | Private | Private | New | 48.7878 | -106.3862 | 3117 | Valley | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-25 | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-08-21 | 2024-09-30 | FPPA >160
Larslan SW | Larslan SW | O-03 | LLNM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.5267 | -106.243 | 2936 | Valley | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-26 | 2024-09-30
Nashua NE | Nashua NE | O-04 | NUAM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.1961 | -106.3213 | 2380 | Valley | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-24 | 2024-09-30
Scotsman Coulee | Scotsman Coulee | O-05 | SCTM8 | N | Private | Private | New | 47.9293 | -106.167 | 2512 | McCone | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-05-18 | 2026-01-09 |  |  | 2025-09-30
Weldon SW | Weldon SW | O-06 | WLDM8 | N | Private | Private | New | 47.5536 | -106.1103 | 2436 | McCone | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Van Norman S | Van Norman S | O-07 | VNSM8 | N | Private | Private | New | 47.2142 | -106.2268 | 2527 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Rock Springs N | Rock Springs N | O-08 | RSNM8 | N | Private | Private | New | 46.8853 | -106.2137 | 2769 | Garfield | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-09-15 | 2026-01-09 |  |  | 2025-09-30
Miles City | Miles City | O-09 | MCYM8 |  | Federal | USDA- Agricultural Research Service | Existing | 46.4054 | -105.9543 | 2718 | Custer | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-07 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-08-25 | 2021-11-19
Thurlow | Thurlow | O-10 | THLM8 | N | Private | Private | New | 46.2803 | -106.3119 | 2451 | Rosebud | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO7 MT (FY25) | 2025-04-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-07-25 | 2026-01-09 |  |  | 2025-09-30
Moon Creek Rd |  | O-11 |  |  | Private | Private | New | 45.9341 | -106.1335 | 2571 | Custer | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-03
Ashland E | Ashland E | O-12 | ASAM8 |  | Federal | USFS | New | 45.5733 | -106.1432 | 3185 | Powder River | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-20 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-27 | 2023-09-30
Otter E | Otter E | O-13 | OTRM8 |  | Federal | USFS | New | 45.2469 | -105.9845 | 3936 | Powder River | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-21 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-08-28 | 2023-09-30
Rogers | Arvada 15NE | O-14 | AVMW4 | N | Private | Private | New | 44.9391 | -105.9224 | 3535 | Campbell | Wyoming | Wyoming Mesonet | Complete | Install 2025 | PY5 | TO6 WY (FY25) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-23 | 2023-12-20 |  |  |  | 2025-09-30
Hollcroft | Clearmont 15ESE | O-15 | CLMW4 |  | Private | Private | New | 44.5263 | -106.1102 | 3817 | Johnson | Wyoming | Wyoming Mesonet | Complete | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete | 2024-09-19 | 2022-10-31 | 2025-01-22 | 2025-05-15 | 2024-08-31 | 2024-09-30 | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Blue Butte |  | O16 |  |  | Private | Private | New | 44.2127 | -106.1034 | 4054 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2022-10-31
Arndt | Saddlestring 24E | O-16 | SSMW4 | N | Private | Private | New | 44.2828 | -106.1526 | 3937 | Johnson | Wyoming | Wyoming Mesonet | Complete | Install 2025 | PY5 | TO6 WY (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-08 | 2023-10-12 |  |  |  | 2025-09-30
Falxa |  | O17 |  |  | Private | Private | New | 44.0276 | -106.1749 | 4144 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2023-01-12 |  |  |  |  | Landowner did not agree to location - removing and waiting on new location from Ginger 5/1/2023
Christensen | Linch 24NNE | O-17 | LIMW4 | N | Private | Private | New | 43.9194 | -105.9827 | 4825 | Campbell | Wyoming | Wyoming Mesonet | Complete | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24) | 2024-09-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-27 | 2023-12-20 |  |  |  | 2025-09-30
Morse | Linch | O-18 | LHMW4 | N | Private | Private | New | 43.6053 | -106.1908 | 5016 | Johnson | Wyoming | Wyoming Mesonet | Complete | Install 2025 | PY5 | TO6 WY (FY25) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-09 | 2023-12-20 |  |  |  | 2025-09-30
Round Rock | Edgerton 18E | O-19 | RRMW4 |  | Private | Private | New | 43.4138 | -105.8886 | 5420 | Converse | Wyoming | Wyoming Mesonet | Complete | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete | 2024-08-20 | 2023-01-12 | 2025-01-22 | 2025-05-15 | 2024-08-31 | 2024-09-30 | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Carbert |  | P-02 |  |  | Private | Private | New | 48.9677 | -105.7953 | 2611 | Daniels | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Volt N | Volt N | P-03 | VOTM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.5423 | -105.6621 | 2392 | Roosevelt | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-27 | 2024-09-30
Wolf Point NW | Wolf Point NW | P-04 | WOFM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.1745 | -105.7379 | 2231 | Roosevelt | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-25 | 2024-09-30
Vida W | Vida W | P-05 | VDWM8 | N | Private | Private | New | 47.8009 | -105.7896 | 2536 | McCone | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Circle N | Circle N | P-06 | CRLM8 | N | Private | Private | New | 47.5882 | -105.6622 | 2641 | McCone | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Brockway | Brockway | P-07 | WAYM8 | N | Private | Private | New | 47.3102 | -105.7745 | 2562 | McCone | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Little Sheep Mtn |  | P-08 |  |  | Private | Private | New | 46.8399 | -105.8129 | 2964 | Prairie | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Shirley NW |  | P-09 |  |  | Private | Private | New | 46.6391 | -105.6408 | 2512 | Custer | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Pumpkin Creek N |  | P-10 |  |  | Private | Private | New | 46.2459 | -105.6923 | 2603 | Custer | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Volborg NW |  | P-11 |  |  | Private | Private | New | 45.948 | -105.7733 | 3270 | Custer | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Olive N |  | P-12 |  |  | Private | Private | New | 45.6189 | -105.5396 | 3321 | Powder River | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Biddle NW |  | P-13 |  |  | Private | Private | New | 45.205 | -105.5657 | 3466 | Powder River | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Manor | Recluse 13 NNE | P-14 | RCMW4 | N | Private | Private | New | 44.9575 | -105.6085 | 3976 | Campbell | Wyoming | Wyoming Mesonet | Complete | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO7 WY (FY25) | 2025-04-21 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-19 | 2023-12-20 |  |  |  | 2025-09-30
Mackey |  | P-15 |  | N | Private | Private | New | 44.5701 | -105.6756 | 4124 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2023-10-12
Hines/ Davis |  | P-16 |  | N | Private | Private | New | 44.2787 | -105.6175 | 4920 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2023-10-12
Savageton |  | P-17 |  |  | Private | Private | New | 43.8815 | -105.7153 | 5157 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Install 2026 | PY6 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2024-09-16
Innes |  | P-17 |  | N | Private | Private | New | 43.9356 | -105.8274 | 4973 | Campbell | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO8 WY (FY25) |  |  |  | USACE | Complete | Complete |  | 2023-12-20
Leavitt | Wright 9SW | P-18 | WGMW4 | N | Private | Private | New | 43.6499 | -105.6229 | 5200 | Campbell | Wyoming | Wyoming Mesonet | Complete | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO7 WY (FY25) | 2025-04-21 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-31 | 2023-10-12 |  |  |  | 2025-09-30
Jenne Trail (miller) |  | P19 |  |  | Private | Private | New | 43.378 | -105.5253 | 4845 | Converse | Wyoming | Wyoming Mesonet | Removed | Install 2024 | PY4 | TO4 WY (FY23) |  |  |  |  | Complete | Complete |  | 2022-10-31 |  |  |  |  | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey. ; AKA Miller - Needs to move -working with landowner on new location
Bill 22WNW (Formerly Hardy Ranch) |  | P-19 |  |  | Private | Private | New | 43.3047 | -105.6744 | 5306 | Converse | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY (FY26) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-29
Scobey NW | Scobey NW | Q-02 | SCYM8 |  | Private | Private | New | 48.8602 | -105.4972 | 2467 | Daniels | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-15 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023-09-10 | 2023-09-30
Bredette NE | Bredette NE | Q-03 | BDEM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.5506 | -105.2589 | 2582 | Roosevelt | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-20 | 2024-09-30
Poplar N | Poplar N | Q-04 | PARM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.1785 | -105.2164 | 2137 | Roosevelt | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-21 | 2024-09-30
Vida NE | Vida NE | Q-05 | VDNM8 | N | Private | Private | New | 47.9228 | -105.3495 | 2299 | McCone | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Richey SW |  | Q-06 |  |  | Private | Private | New | 47.5443 | -105.2495 | 2466 | Dawson | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Lindsay SW |  | Q-07 |  |  | Private | Private | New | 47.1945 | -105.2501 | 3036 | Dawson | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Fallon C-B Route |  | Q-08 |  |  | Private | Private | New | 46.8778 | -105.0654 | 2295 | Prairie | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Mildred SW |  | Q-09 |  |  | Private | Private | New | 46.5512 | -105.1359 | 2906 | Prairie | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Mizpah |  | Q-10 |  |  | Private | Private | New | 46.2165 | -105.2056 | 2552 | Custer | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | Private Contractor | In-Progress | In-Progress |  | 2024-08-12
Spring Creek Divide |  | Q-11 |  |  | Private | Private | New | 45.813 | -105.2137 | 3236 | Custer | Montana | MT Climate Office | Candidate | Install 2027 | PY7 | FY27 | [7 empty] | 2025-11-03
Powderville S |  | Q-12 |  |  | Private | Private | New | 45.556 | -105.0648 | 3113 | Powder River | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Broadus SE |  | Q-13 |  |  | Private | Private | New | 45.3072 | -105.2795 | 3199 | Powder River | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Crook 7 | Biddle 18SE | Q-14 | BDMW4 |  | Private | Private | New | 44.953 | -105.0407 | 3895 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | 2022-08-01 | 2022-09-16 | 2023-08-10 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | Incomplete
Devils Tower 16WNW | Devils Tower 16WNW | Q-15 | DTMW4 |  | Private | Private | New | 44.713 | -105.014 | 4012 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | 2022-08-01 | 2022-08-31 | 2023-09-19 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30 | Installed at wrong location - going to be installed at correct location next year (2025)
McNally | Rozet | Q-16 | RZMW4 | N | Private | Private | New | 44.2845 | -105.2143 | 4288 | Campbell | Wyoming | Wyoming Mesonet | Complete | On TO - Install 2025 - location change - need to redo cultural and env | PY5 | TO5 WY (FY24) MOD. | 2024-09-12 | 2025-09-30 | 2026-09-30 | WY State SHPO | Complete | Complete | 2025-07-24 | 2023-10-12 |  |  |  | 2025-09-30
Edwards |  | Q-17 |  | N | Private | Private | New | 43.8993 | -105.2639 | 4780 | Campbell | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO8 WY (FY25) |  |  |  | USACE | Complete | Complete |  | 2023-10-12
Keeline |  | Q-18 |  | N | Private | Private | New | 43.6596 | -105.1074 | 4504 | Campbell | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO8 WY (FY25) |  |  |  | USACE | Complete | Complete |  | 2023-10-12
Dull Center | Bill 8NE | Q-19 | DCMW4 |  | Private | Private | New | 43.2854 | -105.1376 | 4782 | Converse | Wyoming | Wyoming Mesonet | Complete | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete | 2024-09-18 | 2023-01-12 | 2025-01-22 | 2025-05-15 | 2024-08-31 | 2024-09-30 | ENV. - Sage Grouse - Thunder Basin Core Habitat Area - no constuction activties between March 15 - June 3-. Seed distrubed areas with native seed. Implement nesting, perching deterrents ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey. .
Granite Peak |  | Q20 |  |  | Private | Private | New | 42.9384 | -105.2259 | 5040 | Converse | Wyoming | Wyoming Mesonet | Removed | Install 2024 | PY4 | TO4 WY (FY23) |  |  |  |  | Complete | Complete |  | 2023-01-12 |  |  |  |  | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey. ; Needs new language in landuse so needs to go through University to approve changes.
Shawnee (Formerly Rankin) |  | Q-20 |  |  | Private | Private | New | 42.8911 | -105.0301 | 4967 | Converse | Wyoming | Wyoming Mesonet | Candidate | Install 2026 | PY6 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2024-08-31
Redstone | Redstone | R-02 | RSTM8 | Y | Private | Private | Existing | 48.8246 | -104.8417 | 2391 | Sheridan | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE | Complete | Complete 8/30/2021 | 2022-06-28 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-06-23 | 2022-10-28
Medicine Lake W | Medicine Lake W | R-03 | MEDM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.52 | -104.731 | 2474 | Sheridan | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-19 | 2024-09-30
Fort Kipp NW | Fort Kipp NW | R-04 | FTKM8 |  | Tribal Lands | Fork Peck Tribes | New | 48.2234 | -104.7713 | 2110 | Roosevelt | Montana | MT Climate Office | Complete | Install 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | NRCS working on Tribal Permissions | 2022-09-30 | 2025-01-10 | 2025-02-05 | 2024-09-22 | 2024-09-30 | FPPA >160
Elmdale S | Enid N | R-05 |  |  | Private | Private | New | 47.8577 | -104.7429 | 2474 | Richland | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-10-09
Richey SE |  | R-06 |  |  | Private | Private | New | 47.5398 | -104.7597 | 2852 | Dawson | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Stipek NW | Stipek NW | R-07 | SPKM8 | N | Private | Private | New | 47.2611 | -104.726 | 2451 | Rosebud | Montana | MT Climate Office | Complete | Submitted as Candidate in Spring 2024; In-Progress with Env & Cultural | PY5 | TO7 MT (FY25) | 2025-04-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2024-07-25 | 2026-01-09 |  |  | 2025-09-30
Cedar Creek GA |  | R-08 |  |  | Private | Private | New | 46.9201 | -104.6312 | 2558 | Dawson | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Ismay NE |  | R-09 |  |  | Private | Private | New | 46.6027 | -104.6329 | 2832 | Fallon | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Plevna SW |  | R-10 |  |  | Private | Private | New | 46.3243 | -104.6455 | 2890 | Fallon | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Ekalaka W |  | R-11 |  |  | Private | Private | New | 45.9546 | -104.7444 | 3218 | Carter | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Chalk Butte |  | R-12 |  |  | Private | Private | New | 45.6559 | -104.7778 | 3582 | Carter | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Hammond NE |  | R-13 |  |  | Private | Private | New | 45.2766 | -104.8435 | 3650 | Carter | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Crook 6 | Alva 12NNW | R-14 | AVNW4 |  | Private | Private | New | 44.8605 | -104.5444 | 3613 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | 2022-08-01 | 2022-09-16 | 2023-08-08 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Crook 4 | Hulett 6NW | R-15 | HUMW4 |  | Private | Private | New | 44.7389 | -104.6962 | 4442 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | 2022-08-01 | 2022-09-16 | 2023-08-09 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Carlile 2S | Carlile 2S | R-16 | CRMW4 |  | Private | Private | New | 44.4485 | -104.8021 | 4344 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | 2022-08-01 | 2022-08-31 | 2023-06-29 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Upton 9S | Upton 9S | R-17 | UPMW4 |  | Private | Private | New | 43.9643 | -104.6376 | 4373 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | 2022-08-01 | 2022-08-31 | 2023-09-20 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Osage 31SW | Osage 31SW | R-18 | RKMW4 |  | Private | Private | New | 43.6795 | -104.8825 | 4305 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | 2022-08-01 | 2022-08-31 | 2023-07-25 | 2022-08-27 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2024-04-17
Lance Creek 27 NNW |  | R-19 |  |  | Private | Private | New | 43.3945 | -104.7697 | 4335 | Niobrara | Wyoming | Wyoming Mesonet | Candidate | Install 2026 | PY6 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2024-09-12
Kremers | Lance Creek 4ENE | R-20 | LKMW4 | N | Private | Private | New | 43.0416 | -104.5764 | 4536 | Niobrara | Wyoming | Wyoming Mesonet | Complete | Install 2025 | PY5 | TO6 WY (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12
Dooley | Dooley | S-02 | DOOM8 | Y | Private | Private | Existing | 48.8337 | -104.3846 | 2560 | Sheridan | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-06-30 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-06-23 | 2022-10-28
Froid | Froid | S-04 | FROM8 | Y | Federal | USDA | Existing | 48.2579 | -104.4967 | 2170 | Roosevelt | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-06-29 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-06-23 | 2022-10-28
Sidney ARC | Sidney | S-05 | SIYM8 |  | University | Agriculture Research Center - Montana State University | Existing | 47.7823 | -104.2479 | 2260 | Richland | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-24 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-09-12 | 2021-11-19
Crane W | Crane W | S-06 | CRBM8 | N | Private | Private | New | 47.5696 | -104.3186 | 2113 | Richland | Montana | MT Climate Office | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 MT (FY24) | 2024-12-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete |  | 2023-10-12 | 2026-01-09 |  |  | 2025-09-30
Cottonwood |  | S-07 |  |  | Private | Private | New | 47.2064 | -104.2337 | 2498 | Wibaux | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Wibaux S |  | S-08 |  |  | Private | Private | New | 46.9124 | -104.2032 | 2812 | Wibaux | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-09-23
Carlyle SW |  | S-09 |  |  | Private | Private | New | 46.6166 | -104.196 | 3188 | Fallon | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Baker S |  | S-10 |  |  | Private | Private | New | 46.2501 | -104.2904 | 3307 | Fallon | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Mill Iron N |  | S-11 |  |  | Private | Private | New | 45.9323 | -104.1721 | 3177 | Carter | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Belltower |  | S-12 |  |  | Private | Private | New | 45.6486 | -104.3641 | 3249 | Carter | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Albion SE |  | S-13 |  |  | Private | Private | New | 45.1503 | -104.2057 | 3529 | Carter | Montana | MT Climate Office | In-Progress | Submitted Fall 2024 - Cultural and Env. In-Progress | PY6 | TO8 MT (FY25) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete |  | 2024-08-12
Crago | Colony 8NW | S-14 | CGMW4 |  | Private | Private | New | 44.9586 | -104.2547 | 3450 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete | 2024-09-17 | 2023-01-12 | 2025-01-22 | 2025-05-15 | 2024-08-31 | 2024-09-30 | Note this location has BLM land within 0.25 miles to the east and west, but currently avoids it. Also, site is located in sage grouse general habitat, 3+ miles from an active LEK. ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Crook 3 | Aladdin 5SW | S-15 | ALMW4 |  | Private | Private | New | 44.5871 | -104.2483 | 4021 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | 2022-08-01 | 2022-09-16 | 2023-07-27 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Crook 5 | Four Corners 11NW | S-16 | FCMW4 |  | Private | Private | New | 44.1959 | -104.2952 | 5415 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | 2022-08-01 | 2022-09-16 | 2023-06-28 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Weston B | Osage 2ENE | S-17 | OSMW4 |  | Private | Private | New | 43.9938 | -104.3791 | 4544 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | 2022-08-01 | 2022-09-16 | 2023-06-27 | 2022-10-15 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Newcastle 13SSW | Newcastle 13SSW | S-18 | NCMW4 |  | Private | Private | New | 43.6662 | -104.2619 | 3804 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | 2022-08-01 | 2022-08-31 | 2023-07-26 | 2022-08-27 | 2024-02-03 | 2024-07-01 | 2023-09-29 | 2023-09-30
Lance Creek 22NE |  | S-19 |  |  | Private | Private | New | 43.2283 | -104.2957 | 3971 | Niobrara | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY (FY26) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-09-14
Lusk 15NE |  | S-20 |  |  | Private | Private | New | 42.9451 | -104.2824 | 4403 | Niobrara | Wyoming | Wyoming Mesonet | Candidate | Install 2026 | PY6 | TO9 WY (FY26) |  |  |  | USACE | Complete | Complete |  | 2024-09-13
Van Tassell 9WNW |  | S-21 |  |  | Private | Private | New | 42.6975 | -104.2623 | 4867 | Niobrara | Wyoming | Wyoming Mesonet | In-Progress | Install 2026 | PY6 | TO 8 WY (FY26) | 2026-03-04 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-09-15
Dagmar 7WSW | Dagmar 7WSW | S-3 | DAGM8 | Y | Private | Private | Existing - Moved >100 Ft (235 ft) | 48.5555 | -104.3476 | 2109 | Sheridan | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-05 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Marmarth 2N | Marmarth 2N | T-10 | MRNN8 | N | Private | Private | New | 46.3228 | -103.9374 | 2840 | Slope | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-28 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-06-14 | 2023-09-30
Ludlow 16W | Ladner | T-11 | LNMS2 |  | Private | Private | New | 45.8268 | -103.7172 | 3134 | Harding | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-08-30 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-09-13 | 2023-09-30
Buffalo 8W | Buffalo | T-12 | BOMS2 | N | Private | Private | New | 45.571 | -103.7185 | 933 | Harding | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-09 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-09-18 | 2025-09-30
Camp Crook 9SSW | Camp Crook | T-13 | CCMS2 |  | Private | Private | New | 45.4235 | -104.0168 | 3287 | Harding | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-26 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-09-19 | 2024-09-30
Belle Fourche 18N | Center of the Nation | T-14 | USAS2 | N | Private | Private | New | 44.9673 | -103.7712 | 964 | Butte | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-29 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-09-25 | 2025-09-30
Spearfish 4NNW | Spearfish | T-15 | SPMS2 |  | Private - Easement | NRCS EQIP Program | New | 44.5657 | -103.9164 | 3407 | Lawrence | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-09-19 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-09-20 | 2023-09-30
Lead 1SE |  | T-16 |  | No | State | SD Science & Tehcnology Authority | New | 44.3434 | -103.7521 | 1542 | Lawrence | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Jewel Cave |  | T-18 | JWLS2 |  | Federal | NPS - Jewel Cave National Monument | Existing | 43.7343 | -103.8278 | 5672 | Custer | South Dakota | SD Mesonet | Candidate | Awarded in Sept 2021; Extended Installation POP to 2024 | Unk | TO3 SD (FY21) Mod. | 2022-08-15 | 2024-09-30 | 2025-09-30 | NPS | Complete | Complete 8/30/2021 | Push to 2024 | 2022-08-27 |  |  |  |  | NPS decided they needed a a more complete tribal review & Special Use Permit (SUP). Has delayed the install on this. CIRE Proj coord. Has been in direction communication with Mike Wiles from NPS to keep moving forward.
Edgemont | Edgemont | T-19 | EDTS2 |  | Private | Private | Existing | 43.4737 | -103.9717 | 3710 | Fall River | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-29 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-20 | 2021-12-15
Fortuna | Fortuna | T-2 | FTUN8 | Y | Private | Private | Existing | 48.9637 | -103.8058 | 2246 | Divide | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-07 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-09 | 2021-11-19
Provo 11S | Provo | T-20 | PVMS2 |  | Private | Private | New | 43.0375 | -103.7986 | 3797 | Fall River | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE | Complete | Complete | 2022-10-17 | 2022-08-27 | 2024-02-28 | 2024-02-28 | 2022-10-23 | 2022-09-30
Harrison 2SW | Harrison 2SW | T-21 | HAUN1 | N | University | Board of Regents (UNL) | New | 42.664 | -103.898 | 4910 | Sioux | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-08 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-17 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.; Swift fox measures requied by NE Game and Parks.
Harrison 15S | Harrison 15S | T-22 | HIMN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.4819 | -103.7894 | 4713 | Sioux | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-28 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey.
Grenora | Grenora | T-3 | GREN8 | Y | Private | Private | Existing | 48.735 | -103.8812 | 2108 | Divide | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-08 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-08 | 2021-11-19
Williston | Williston | T-4 | WLLN8 | Y | University | NDSU | Existing | 48.1331 | -103.739 | 2132 | Williams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-22 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-15 | 2021-11-19
Buford 3SE | Buford 3SE | T-5 | BFDN8 | N | Private | Private | New | 47.9707 | -103.9259 | 1868 | Wiliams | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-09 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-08-14 | 2024-09-30 | FPPA Form submitted to NRCS
Poker Jim | Poker Jim | T-6 | PKJN8 | Y | Private | Private | Existing | 47.5025 | -103.6559 | 2092 | McKenzie | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-18 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-07-12 | 2023-09-30
Sentinel Butte 10N | Sentinel Butte 10N | T-7 | SLBN8 | Y | Private | Private | Existing | 47.0669 | -103.7933 | 2736 | Golden Valley | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-11 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-07-12 | 2023-09-30
Beach | Beach | T-8 | BCHN8 | Y | Private | Private | Existing | 46.7894 | -103.9662 | 2932 | Golden Valley | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete | 2022-07-06 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-06-09 | 2022-09-28
Davis Dam 2NW | Davis Dam 2NW | T-9 | DVDN8 | N | Private | Private | New | 46.5641 | -103.6971 | 2906 | Slope | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-06-23 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-06-14 | 2023-09-30
Bowman | Bowman | U-10 | BOMN8 | Y | Private | Private | Existing | 46.1997 | -103.473 | 3032 | Bowman | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-28 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-09-09 | 2021-11-19
Ludlow |  | U-11 |  |  | Private | Private | New | 45.8333 | -103.3707 | 3075 | Harding | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-15
Antelope | Antelope | U-12 | ATRS2 |  | Private | Private | Existing | 45.5193 | -103.2888 | 2903 | Harding | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 8/19/2022 (Orig. Sampling in 2019) | n/a | 2024-02-28 | 2024-02-28 | 2022-07-21 | 2022-08-20
Redig 3N | Redig | U-13 | RDMS2 |  | Private | Private | New | 45.3195 | -103.5495 | 3168 | Harding | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-08-31 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-09-19 | 2023-09-30
Newell 13NNW |  | U-14 |  |  | Private | private | New | 44.9002 | -103.4878 |  | Butte | South Dakota | SD Mesonet | In-Progress | Submitted as candidate site Nov 2021; Waiting on RE | PY6 | TO10 SD (FY26) | 2026-03-02 | 2027-09-30 | 2028-09-30 | USACE | Complete | Complete
Nisland | Nisland | U-15 | NISS2 |  | Federal | BOR | Existing | 44.6783 | -103.5606 | 2906 | Butte | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/25/2021 | 6/12/2022 (Orig. Sampling in 2019) | n/a | 2024-02-28 | 2024-02-28 | 2022-06-22 | 2022-08-20
Sturgis | Sturgis | U-16 | STMS2 |  | State | South Dakota State - University Reseach Farm | Existing | 44.4245 | -103.3793 | 3237 | Meade | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2019-06-25 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-15
Custer State Park 5SSE |  | U-18 |  |  | State | SD Game Fish & Parks | New | 43.6532 | -103.3754 | 3903 | Custer | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-01
Hot Springs 7SSE |  | U-19 |  |  | Federal | US Bureau of Reclamation and SD State Game Fish Parks | New | 43.3461 | -103.4142 | 3244 | Fall River | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | US BOR |  |  |  | 2025-07-01 |  |  |  |  | USBOR owned and managed Angostura Reservoir (requires SUP), SD Game Fish & Parks managed Angostura recreation and game production area - additional coordination needed to determine requirements of both agencies.
Smithwick 4SW |  | U-19 |  |  | Private | private | New | 43.2666 | -103.2909 | 3365 | Fall River | South Dakota | SD Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned | [12 empty] | Landowner backed out - Removed
Oelrichs 11SSW | Oelrichs | U-20 | OEMS2 |  | Private | Private | New | 43.0409 | -103.3476 | 3592 | Fall River | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-10 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-07-26 | 2023-09-30
Whitney 4SW | Whitney 4SW | U-21 | WHUN1 | N | University | Board of Regents (UNL) | New | 42.7423 | -103.3179 | 3492 | Dawes | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-09 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-17 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.
Marsland 6S | Marsland 6S | U-22 | MAUN1 | N | State | Nebraska School Lands | New | 42.3557 | -103.3313 | 4525 | Box Butte | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-08 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-12 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.; Swift fox measures requied by NE Game and Parks.
Scottsbluff 16NE |  | U-23 | SSEN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.0056 | -103.4033 | 1360.38 | Sioux | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Ray | Ray | U-3 | RAYN8 | Y | Private | Private | Existing | 48.4009 | -103.169 | 2316 | Williams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-09 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-10 | 2021-11-19
Hofflund | Hofflund | U-4 | HOFN8 | Y | University | NDSU | Existing | 48.1644 | -103.1082 | 1906 | Williams | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-10 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-08-13 | 2024-09-30
Watford City 3SW | Watford City 3SW | U-5 | WFDN8 | Y | County | McKenzie County | Existing - Moved >100 Ft (30,375 ft. ) | 47.7793 | -103.3468 | 2180 | McKenzie | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-17 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Grassy Butte 2E | Grassy Butte 2E | U-6 | GSBN8 | Y | Private | Private | Existing | 47.3865 | -103.2062 | 2688 | McKenzie | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-21 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-07-12 | 2022-09-28
Fairfield | Fairfield | U-7 | FLDN8 | Y | Private | Private | Existing | 47.1253 | -103.2432 | 2682 | Billings | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-22 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023-07-13 | 2023-09-30
Pyramid Park | Pyramid Park | U-8 | PMPN8 | N | University | NDSU | New | 46.7814 | -103.3584 | 2620 | Billings | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-13 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-04-23 | 2024-09-30
Amidon | Amidon | U-9 | AIDN8 | Y | Private | Private | Existing | 46.4885 | -103.316 | 2883 | Slope | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-29 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-09-08 | 2021-11-19
Cedar Lake 3W | Cedar Lake 3W | V-10 | CDLN8 | N | Private | Private | New | 46.2839 | -103.0284 | 2766 | Slope | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-17 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-06-04 | 2024-09-30 | FPPA Form submitted to NRCS
Ralph 11NE | Ralph | V-11 | RAMS2 |  | Private | Private | New | 45.9061 | -102.9228 | 2742 | Perkins | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE | Complete | Complete | 2022-10-20 | 2022-08-27 | 2024-02-28 | 2024-02-28 | 2022-11-01 | 2022-09-30
Lodgepole 10SSW |  | V-12 |  |  | State | SD School & Public Lands | New | 45.6837 | -102.7508 | 2596 | Perkins | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-07-15
Prairie City 15SSW | Prairie City | V-13 | PCMS2 |  | Private | Private | New | 45.3388 | -102.9195 | 2835 | Perkins | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-08-31 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-09-14 | 2023-09-30
Opal 8WNW | Mud Butte | V-14 | MBMS2 |  | Private | private | New | 44.9196 | -102.7539 | 2645 | Meade | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-24 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-06-26 | 2024-09-30
Union Center 16NW | Union Center NW | V-15 | UCMS2 |  | Private | private | New | 44.7047 | -102.8964 | 2810 | Meade | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-18 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-06-27 | 2024-09-30
New Underwood 10N | New Underwood | V-16 | NUMS2 | N | Private | Private | New | 44.235 | -102.8288 | 867 | Meade | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-18 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-05-14 | 2025-09-30
Caputa | Caputa | V-17 | CPTS2 |  | Private | Private | Existing | 44.0008 | -103.0008 | 2931 | Pennington | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-30 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-18 | 2021-11-19
Fairburn 15ENE | Hermosa | V-18 | HSMS2 |  | Private | Private | New | 43.7387 | -102.9226 | 2939 | Custer | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-27 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-06-13 | 2024-09-30
Oral 16ENE |  | V-19 |  |  | Private on Tribal Lands | Oglala Sioux Tribe - Pine Ridge Resrvation | New | 43.1798 | -102.9891 | 3082 | Oglala Lakota | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | SDSU Coordination with OST |  |  |  | 2025-09-30 |  |  |  |  | Within Pine Ridge Reservation, will need THPO permits to survey. No prior survey.
Oelrichs 11ESE | Fall River SE | V-20 | FLMS2 |  | Private | Private | New | 43.1003 | -103.0547 | 3353 | Fall River | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE | Complete | 2022-08-31 | 2023-07-11 | 2022-11-15 | 2024-02-28 | 2024-02-28 | 2023-07-26 | 2023-09-30
Hay Spring 12W | Hay Spring 12W | V-21 | HSUN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.6146 | -102.9095 | 4236 | Dawes | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-06 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-18 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.; Swift fox measures requied by NE Game and Parks.
Hemingford 9NE | Hemingford 9NE | V-22 | HEUN1 | N | State | Nebraska School Lands | New | 42.4087 | -102.9395 | 4088 | Box Butte | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-07 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-18 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.
Alliance 3SW | Alliance 3SW | V-23 | ALUN1 | N | State | Nebraska School Lands | New | 42.058 | -102.894 | 3959 | Box Butte | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-07 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-19 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.
Columbus 12S | Columbus 12S | V-3 | CBSN8 | N | Private | Private | Existing | 48.7315 | -102.7011 | 2449 | Burke | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-15 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Dry Fork 1SE | Dry Fork 1SE | V-4 | DFKN8 | Y | County | Williams County | Existing - Moved < 50 ft | 48.2408 | -102.894 | 2140 | Williams | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-20 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Keene 5SW | Keene 5SW | V-5 | KEEN8 | Y | Private | Private | Existing | 47.8938 | -103.0482 | 2346 | McKenzie | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-26 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-07-13 | 2022-09-28
Little Missouri | Little Missouri | V-6 | LMPN8 | N | Private | Private | New | 47.5574 | -102.7567 | 2436 | Dunn | North Dakota | NDAWN | Complete | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-08 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30 | Received a 3rd location on April 15 2024 - In review with USACE team
Manning 4SW | Manning 4SW | V-7 | MNNN8 | N | University | NDSU | New | 47.1925 | -102.8325 | 2442 | Dunn | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-16 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-04-25 | 2024-09-30
Dickinson | Dickinson | V-8 | DKSN8 | Y | University | NDSU | Existing | 46.8948 | -102.8131 | 2557 | Stark | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete | 2022-08-03 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-06-10 | 2022-09-29
New England 5W | New England 5W | V-9 | NEDN8 | N | Private | Private | New | 46.5264 | -102.968 | 2718 | Slope | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-03 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-06-15 | 2023-09-30
Mott | Mott | W-10 | MATN8 | Y | Private | Private | Existing | 46.3798 | -102.322 | 2473 | Hettinger | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-30 | 2022-08-27 | 2022-01-31 | 2022-03-04 | 2021-07-01 | 2021-11-19
Hettinger | Hettinger | W-11 | HTGN8 | Y | University | NDSU | Existing | 46.0126 | -102.6453 | 2758 | Adams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-15 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-30 | 2021-11-19
Bison | Bison | W-12 | BSNS2 | Y | Private | Private | Existing | 45.5182 | -102.4866 | 829 | Perkins | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-09 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-07-24 | 2025-09-30
Bison 20SSE | Faith NW | W-13 | FAMS2 | N | Private | Private | New | 45.2552 | -102.3204 | 736 | Perkins | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-17 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-07-23 | 2025-09-30
Union Center | Union Center | W-15 | UNIS2 |  | City | Non-federal airport property | Existing | 44.5665 | -102.671 | 2938 | Meade | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-22 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-02 | 2021-12-15
Elm Springs 2E | Elm Springs | W-16 | ESMS2 | N | Private | Private | New | 44.3142 | -102.486 | 814 | Meade | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-12 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-05-09 | 2025-09-30
Wasta 4SE |  | W-17 |  | No | Private | Private | New | 44.0374 | -102.38 | 840 | Pennington | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Scenic 6ESE | Scenic | W-18 | SNMS2 |  | Private | Private | New | 43.7574 | -102.4421 | 2679 | Pennington | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-25 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-06-12 | 2024-09-30
Manderson 16N | Porcupine | W-19 | PPMS2 | N | Tribal Lands | Oglala-Sioux Tribe - Pine Ridge Reservation | New | 43.4759 | -102.5022 | 840 | Oglala Lakota | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-29 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-08-21 | 2025-09-30
Pine Ridge 3NE | Pine Ridge | W-20 | PNMS2 | N | Tribal Lands | Oglala-Sioux Tribe - Pine Ridge Reservation | New | 43.046 | -102.4652 | 1039 | Oglala Lakota | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-31 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-08-20 | 2025-09-30
Rushville 2SE | Rushville 2SE | W-21 | RSVN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.7122 | -102.4373 | 3811 | Sheridan | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-05 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-17 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.
Hay Springs 22S | Hay Springs 22S | W-22 | HSPN1 | N | University | Board of Regents (UNL) | New | 42.3697 | -102.6491 | 3924 | Sheridan | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-06 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-18 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.
Lakeside 3NE |  | W-23 | LKMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.1049 | -102.4041 | 1193.51 | Sheridan | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Powers Lake 7SE | Powers Lake 7SE | W-3 | POLN8 | Y | Private | Private | Existing | 48.4841 | -102.5608 | 2298 | Mountrail | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-10 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-08-28 | 2024-09-30 | FPPA Form submitted to NRCS; ENV. - Dakota Skipper - If habitat is determined to be present by surveys conducted in the summer of 2023, occupancy surveys shall be conducted by a USFWS permitted surveyor following the 2022 Dakota Skipper Survey Protocol.
Ross 9SE | Stanley 8SW | W-4 | STYN8 | N | Private | Private | New | 48.1962 | -102.4653 | 2341 | Mountrail | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-11 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-08-27 | 2024-09-30
Liberty 5E | Liberty 5E | W-5 | LBTN8 | Y | Private on Tribal Lands | Fort Berthold Reservation | Existing | 47.9143 | -102.2162 | 2041 | Mountrail | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-11 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-06-19 | 2024-09-30 | FPPA Form submitted to NRCS
Halliday | Halliday | W-6 | HLDN8 | N | Private | Private | New | 47.4189 | -102.3194 | 2260 | Dunn | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO7 ND (FY25) | 2025-08-13 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-25 | 2024-08-26 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Werner Mandaree 9E |  | W-6 |  |  | County | Dunn County | New | 47.4015 | -102.5039 | 2220 | Dunn | North Dakota | NDAWN | Removed | Re-Submitted as Candidate in April 2024 in replacement for Mandaree; In-Progress with Env. & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress |  | 2022-09-29 |  |  |  |  | April 19 2024 update - NDAWN sent replacement on different property. Now called Werner. CUL. - Likely going to be removed bc on historic site of some kind. Working with landowner to see other options. July 24 ENV. - Dakota Skipper - If habitat is determined to be present by surveys conducted in the summer of 2023, occupancy surveys shall be conducted by a USFWS permitted surveyor following the 2022 Dakota Skipper Survey Protocol.
Marshall 5N | Marshall 5N | W-7 | MRHN8 | N | ND State | ND Department Trust Lands | New | 47.2056 | -102.3452 | 2225 | Dunn | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-04 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Taylor 6NW | Taylor 6NW | W-8 | TAYN8 | N | Private | Private | New | 46.9556 | -102.5178 | 2208 | Stark | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-26 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Lefor 10SE | Lefor 10SE | W-9 | LEFN8 | N | Private | Private | New | 46.5883 | -102.3851 | 2564 | Hettinger | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-03 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-06-05 | 2024-09-30 | FPPA Form submitted to NRCS
Pretty Rock 2E | Pretty Rock 2E | X-10 | PTON8 | N | Private | Private | New | 46.1597 | -101.7705 | 2514 | Grant | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-10-17 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023-08-02 | 2023-09-30
Meadow |  | X-12 |  |  | Private on Tribal Lands | Standing Rock Reservation | New | 45.5735 | -101.9842 |  | Corson | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Nov 2021; Pending Issues | Unk | Unk. Timeline |  |  |  | USACE Staff | Complete | Complete
Glad Valley 12SW |  | X-13 |  | No | State & Tribal Lands | SD School & Public Lands & Northern Cheyenne Indian Reservation | New | 45.3042 | -101.9816 | 2390 | Ziebach | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Faith 11S |  | X-14 |  | No | Private | Private | New | 44.8642 | -102.0422 | 722 | Meade | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Milesville 11W | Milesville | X-15 | MVMS2 |  | Private | FPPA Prime Farmland | New | 44.4749 | -101.8991 | 2338 | Haakon | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE | Complete | Complete | 2022-10-04 | 2022-08-27 | 2024-02-28 | 2024-02-28 | 2022-10-15 | 2022-09-30
Burbank 6NNE |  | X-16 |  | No | Commercial | Commercial | New | 42.8512 | -96.7905 | 1239 | Union | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Lemmon 2S |  | X-16 |  | No | Private | Private | New | 45.9129 | -102.1549 | 2533 | Perkins | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Faulkton 4NNE |  | X-16 |  | No | Private | Private | New | 45.0859 | -99.0846 | 1544 | Faulk | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Broadland |  | X-16 |  | No | Private | Private | New | 44.4933 | -98.3348 | 1309 | Beadle | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Webster 2E |  | X-16 |  | No | Private | Private | New | 45.339 | -97.4739 | 1874 | Day | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Emery 5SSW |  | X-16 |  | No | Private | Private | New | 43.5393 | -97.6676 | 1369 | Hanson | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Fairview 2SSW |  | X-16 |  | No | Private | Private | New | 43.1982 | -96.5089 | 1449 | Lincoln | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Saint Charles 2SSW |  | X-16 |  | No | Private | Private | New | 43.1002 | -99.1081 | 2136 | Gregory | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-11-17
Wall 11N |  | X-16 |  | No | Private | Private | New | 44.2119 | -102.1968 | 813 | Pennington | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | USACE |  |  |  | 2025-05-11
Cottonwood | Cottonwood | X-17 | CTWS2 |  | State | South Dakota State - University Reseach Farm | Existing | 43.9599 | -101.8539 | 2365 | Jackson | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2019-06-05 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-15
Interior 4SSW |  | X-18 |  |  | Tribal Lands | Oglala Sioux Tribe | New | 43.664 | -102.001 | 2645 | Jackson | South Dakota | SD Mesonet | Candidate | Install 2026 | PY6 | TO 10 SD (FY26) |  |  |  | SDSU Coordination with OST |  |  |  | 2025-07-15 |  |  |  |  | Within Pine Ridge Reservation, will need THPO permits to survey. No prior survey.
Kyle | Kyle | X-19 | KYMS2 | N | Tribal Lands | Oglala-Sioux Tribe | New | 43.4172 | -102.1711 | 889 | Oglala Lakota | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-29 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-08-22 | 2025-09-30
Batesland | Batesland | X-20 | BLMS2 | N | Tribal Lands | Oglala-Sioux Tribe | New | 43.1311 | -102.0994 | 1045 | Bennett | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-31 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-08-20 | 2025-09-30
Gordon 13SE | Gordon 13SE | X-21 | GONN1 | N | University | Board of Regents (UNL) | New | 42.6483 | -102.0689 | 3625 | Sheridan | Nebraska | NE Mesonet | Complete | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-05 | 2022-09-29 | 2024-12-20 | 2025-01-21 | 2024-09-17 | 2024-09-30 | ENV. - Whooping Crane surveys Required by USFWS.
Sheridan 1 | Ellsworth 16NE | X-22 | ESWN1 | N | State | State Educational Lands and Funds - Leased Public | New | 42.2803 | -102.1628 | 4130 | Sheridan | Nebraska | NE Mesonet | Complete | Install 2023 | PY2 | TO 1 NE (FY21) Mod. | 2022-11-01 | 2022-12-31 | 2023-12-31 | USACE Contractor | Complete | Complete | 2023-09-07 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023-10-04 | 2023-10-30 | Replacement for Longpine on TO1. Modification. Supposed to be by Dec 2022 but delayed through the summer. O&M date will still end in Dec. 2023
Shell Lake | Shell Lake | X-4 | SHLN8 | Y | Private | Private | Existing | 48.1501 | -102.0727 | 2058 | Mountrail | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-22 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-08-10 | 2023-09-30
Garrison | Garrison | X-5 | GANN8 | Y | Private | Private | Existing | 47.7102 | -101.6795 | 2200 | McLean | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-08-16 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-08-03 | 2022-09-28
Zap 11N | Zap 11N | X-6 | ZPPN8 | N | Private | Private | New | 47.4367 | -101.9714 | 2188 | Mercer | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-05 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-07-16 | 2024-09-30 | FPPA Form submitted to NRCS
Hazen | Hazen | X-7 | HAZN8 | Y | Private | Private | Existing | 47.3018 | -101.6792 | 1849 | Mercer | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | 2021-02-08 | 2021-08-23 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-08-10 | 2021-11-19
Glen Ullin (Hebron) | Glen Ullin (Hebron) | X-8 | HBNN8 | N | Private | Private | New | 46.8045 | -102.0759 | 2450 | Morton | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-10 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023-07-13 | 2023-09-30
Elgin 10NW | Elgin 10NW | X-9 | ELIN8 | N | Private | Private | New | 46.5011 | -101.9861 | 2387 | Grant | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-09-06 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-06-06 | 2024-09-30
St. Gertrude 12S | St. Gertrude 12S | Y-10 | SGTN8 | N | Private | Private | New | 46.1183 | -101.3329 | 1948 | Grant | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-09 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Isabel 3WSW | Isabel | Y-13 | ISMS2 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.3864 | -101.4925 | 2360 | Ziebach | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) | 2024-09-04 | 2024-09-30 | 2025-09-30 | Tribe | Complete | Complete | 2024-10-02 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-09-11 | 2024-09-30
Lantry 5NNW | Lantry | Y-14 | LTMS2 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.087 | -101.4843 | 2329 | Dewey | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) | 2024-09-04 | 2024-09-30 | 2025-09-30 | Tribe | Complete | Complete | 2024-10-02 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-09-12 | 2024-09-30 | FPPA Site - Score >160; AD-1006 form submitted
Cherry Creek 10NE | Cherry Creek | Y-15 | CHMS2 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 44.7079 | -101.3658 | 2042 | Ziebach | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) | 2024-09-04 | 2024-09-30 | 2025-09-30 | Tribe | Complete | Complete | 2024-09-30 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-08-29 | 2024-09-30 | FPPA Site - Score >160; AD-1006 form submitted
Philip 10 NNE | Philip | Y-16 | PLMS2 | N | Private | Private | New | 44.1817 | -101.5261 | 711 | Haakon | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-06-03 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-06-11 | 2025-09-30
Kadoka 5WNW | Kadoka | Y-17 | KDMS2 |  | Private | Private | New | 43.874 | -101.5916 | 2355 | Jackson | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-07-25 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-07-11 | 2024-09-30
Wanblee 5E | Wanblee | Y-18 | WBMS2 | N | Tribal Lands | Oglala-Sioux Tribe | New | 43.5885 | -101.5609 | 827 | Jackson | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-07-29 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-09-10 | 2025-09-30
Martin 4ENE | Martin | Y-19 | MATS2 |  | Private on Tribal Lands | Oglala-Sioux Tribe - Pine Ridge Reservation | New | 43.1991 | -101.6512 | 3197 | Bennett | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-06-11 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-05-30 | 2024-09-30 | FPPA Site - Score >160; AD-1006 form submitted
Merriman 7E | Merriman 7E | Y-20 | MEAN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.9178 | -101.5621 | 3304 | Cherry | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-05 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey.
Cherry 1 | Merriman 21S | Y-21 | MEIN1 | N | State | State Educational Lands and Funds - Leased Public | New | 42.6154 | -101.7244 | 3619 | Cherry | Nebraska | NE Mesonet | Complete | Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-09-07 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023-10-03 | 2023-10-30
Max 3N | Max 3N | Y-5 | MXAN8 | N | Private | Private | New | 47.87 | -101.3143 | 2180 | Ward | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-27 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-06-18 | 2024-09-30 | FPPA Form submitted to NRCS
Pick City 8SW | Pick City 8SW | Y-6 | PCDN8 | N | Private | Private | New | 47.4747 | -101.6123 | 2045 | Mercer | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-15 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023-08-09 | 2023-09-30
Center 5S | Center 5S | Y-7 | CNIN8 | Y | Private | Private | Existing - Moved < 50 ft | 47.0519 | -101.2794 | 2026 | Oliver | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-10 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
New Salem 6SE | New Salem 6SE | Y-8 | NSLN8 | N | Private | Private | New | 46.7678 | -101.342 | 2186 | Morton | North Dakota | NDAWN | Complete | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | 2024-08-26 | 2022-09-29 | 2024-12-03 | 2025-01-29 | 2024-06-27 | 2024-09-30
Carson | Carson | Y-9 | CSRN8 | Y | Private | Private | Existing | 46.443 | -101.3738 | 2107 | Grant | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-12 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-06-29 | 2021-11-19
Shields 2N | Shields 2N | Z-10 | SHDN8 | N | Private | Private | New | 46.2639 | -101.1247 | 1934 | Grant | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO7 ND (FY25) | 2025-08-13 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-12 | 2025-02-21 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Selfirdge 8N |  | Z-10 |  |  | ND State | ND Department Trust Lands | New | 46.1611 | -100.9479 | 2060 | Sioux | North Dakota | NDAWN | Removed | Install 2025 | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress |  | 2023-09-13
Timber Lake | Timber Lake | Z-12 | TIMS2 |  | City & Tribal | Cheyenne River Reservation | Existing | 45.4166 | -101.085 | 2196 | Dewey | South Dakota | SD Mesonet | Complete | Install 2021; Sub For Faulkton on TO1 | PY1 | TO1 SD (FY20) Mod | 2021-12-03 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2019-06-27 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-12-18 | 2021-12-15
Parade 11N |  | Z-13 |  | No | Private on Tribal Lands | Northern Cheyenne Indian Reservation | New | 45.1785 | -101.1195 | 1829 | Dewey | South Dakota | SD Mesonet | Candidate | Install 2027 | PY7 | FY27 |  |  |  | USACE |  |  |  | 2025-09-30
Parade | Eagle Butte | Z-14 | EGBS2 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.0239 | -101.0771 | 2412 | Dewey | South Dakota | SD Mesonet | Complete | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) | 2024-09-04 | 2024-09-30 | 2025-09-30 | Tribe | Complete | Complete | 2024-10-07 | 2023-11-30 | 2024-12-06 | 2025-01-17 | 2024-09-26 | 2024-09-30 | FPPA Site - Score >160; AD-1006 form submitted
Hayes 14NNW | Hayes N | Z-15 | HYMS2 | N | Private | Private | New | 44.5596 | -101.1418 | 625 | Stanley | South Dakota | SD Mesonet | Complete | Install 2025 | PY5 | TO9 SD (FY25) | 2025-05-12 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-05-29 | 2024-01-29 | 2025-11-15 | 2025-12-03 | 2025-06-26 | 2025-09-30
Hayes 7SW | Hayes | Z-16 | HAMS2 |  | Private | FPPA Statewide Importance Farmland | New | 44.3123 | -101.1292 | 2025 | Stanley | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE | Complete | Complete | 2022-10-13 | 2022-08-27 | 2024-02-28 | 2024-02-28 | 2022-10-16 | 2022-09-30
Midland 3ENE | Midland | Z-17 | MLMS2 |  | Private | Private | New | 44.0851 | -101.091 | 1851 | Haakon | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-09-21 | 2022-10-15 | 2024-02-28 | 2024-02-28 | 2023-09-28 | 2023-09-30
Norris 10NNE | Norris | Z-18 | NOMS2 |  | Private | Private | New | 43.5998 | -101.1013 | 2454 | Mellette | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE | Complete | Complete | 2022-10-06 | 2022-08-27 | 2024-02-28 | 2024-02-28 | 2022-10-24 | 2022-09-30
Spring Creek 12WNW | Tuthill | Z-19 | THMS2 |  | Private on Tribal Lands | Pine Ridge Reservation | New | 43.206 | -101.2295 | 5423 | Bennett | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 |  | Complete | 2022-08-31 | 2023-07-27 | 2022-11-15 | 2024-02-28 | 2024-02-28 | 2023-08-16 | 2023-09-30
Cody 4SW | Cody 4SW | Z-20 | CODN1 | N | State | Nebraska Board of Educational Lands and Funds | New | 42.8773 | -101.272 | 3129 | Cherry | Nebraska | NE Mesonet | Complete | Install 2025 | PY5 | TO 4 NE (FY24) | 2024-09-23 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-06 | 2023-09-23 | 2025-12-03 | 2026-01-23 |  | 2025-09-30 | Whooping crane - Don't install or do NRCS work before April 29th or after Oct 9. American Burying Beetle - NRCS pits kept to a minimum: 3.5 ft widex7 ft longx 3.5 ft deep; NRCS pits should be backfilled same day immediately following sampling & restored to preconstruction condition: MBTA - no construction between Apil 1 to July 15 - if done, then need to do a pre-construction survey. Bald & Golden Eagle Protection Act - Should a bald or golden eagle nest be detected within 0.5 miles of the project site prior to installation, USACE shall be contacted, and the National Bald and Golden Eagle Management Guidelines (FWS, 2007) will be followed.
Cody 21S |  | Z-21 | CDMN1 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.6263 | -101.2537 | 988.93 | Cherry | Nebraska | NE Mesonet | In-Progress | Install 2026 | PY6 | TO 5 NE (FY25) | 2025-09-12 | 2026-09-30 | 2027-09-30 | USACE | Complete | Complete |  | 2024-08-28
Benedict 4SE | Benedict 4SE | Z-5 | BNDN8 | N | Private | Private | New | 47.7888 | -101.0134 | 2069 | McLean | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-08-01 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30
Turtle Lake | Turtle Lake | Z-6 | TURN8 | Y | Private | Private | Existing | 47.5679 | -100.9153 | 1927 | McLean | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-08-16 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-08-02 | 2022-09-28
Sanger | Sanger | Z-7 | SNRN8 | N | Private | Private | New | 47.1668 | -100.9891 | 1689 | Oliver | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-25 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023-08-08 | 2023-09-30
Mandan | Mandan | Z-8 | MMDN8 | Y | Federal | USDA | Existing | 46.7736 | -100.9139 | 1907 | Morton | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-08-18 | 2021-09-30 | 2022-12-02 | 2023-01-10 | 2022-08-15 | 2022-09-28
St. Anthony 8SW | St. Anthony 8SW | Z-9 | SATN8 | N | Private | Private | New | 46.5128 | -101.0065 | 2089 | Morton | North Dakota | NDAWN | Complete | Install 2025 | PY5 | TO6 ND (FY24) | 2024-11-08 | 2025-09-30 | 2026-09-30 | USACE | Complete | Complete | 2025-09-12 | 2023-09-13 | 2025-10-29 | 2026-01-30 |  | 2025-09-30

## Categories
Attribute | Site | Grid Cell ID | NWS LI Name | Part of NMP? | Land Ownership Category | Landownership Detail | Site Type | Latitude | Longitude | Elevation | County | State | Owner | Site Status | Station Status Note | Project Year (PY) | Installation Task Order & Fiscal Year | Installation Task Order Date of Award | Contract Installation Deadline | O&M Period Of Performance | Operational Date | Cultural Survey and Sec 106 Responsible party | Sec 106 Status | NEPA Status (Date REC Signed) | NRCS Soil Survey Status | Candidate Site Form - Date Received | Station Report | Annual Report | Equipment Installation Complete | Data Transmission
Description | Identifier given by states - some names end in a number and direction which is the distance in miles and cardinal direction to a major city | Identifier for the UMRB Network Grid Cell that the station is assigned | 5-digit name given by the National Weather Service for sites. For sites that are not yet in the network- these are proposed names by the Mesonet | Is the site part of the National Mesonet Program? | Broad Category for landownership | Detail on landownership such as agency, tribe or other entity. | Describes if site is a new or exisiting site or existing but moved more than 100 feet. | Latitude for site | Longitude for site | Elevation in feet of station location | County which station is in. | State that site is located | Name of Climate Center that Owns the Station | The category of retrofit of the station. Future Retrofit - Exisiting site within the Network that may or may not be retrofitted. Retrofit complete- A retrofit that is already complete and operational. Retrofit In-Progress - Site is Awarded on a Task Order. Retrofit Planned - Site eligibility is being assessed fo future task order. | A general note to signify where a station is at in the UMRB Network Cycle and if there are any special notes or changes. | The UMRB Network Project Year that the station is associated with | Name of Task Order (TO) that site is included on e.g. TO2 for ND and SD, T01 for NE, etc. and the associated Fiscal Year | Date that the TO was awarded. Null means not yet awarded. | Date that equipment must be installed by and site MUST be operational according to USACE Contract. Null means not yet awarded or unknown. | Date that USACE will provide O&M until. This is typically one year after the installation deadline. | Date that the Mesonets have stated in their work plans that they will have the site operational by. | Repsonsible Party for Completing NEPA and Sec 106 Work. | The status of the cultural clearance process | Date that REC (NEPA) was signed. Null [Not Begun], Complete - Date | Date that the Soil Assessment fieldwork was completed. | Date that the Candidate Site Form (sub for Site Report) was submitted and recevied. | Date that the State Report was submitted and recevied. | Date that the Annual Report was submitted and recevied. | Date that equipment installation is reported completed | Date that data was reported transmitting to USACE or MADIS.
Options (may not be all inclusive for some categories) | Wapiti 6E | I-20 | E.g. SHMW4 | Y (Yes) | Private | University of Wyoming | New |  |  |  |  | Montana | MT Climate Office | Candidate | Notes. | PY1 | Intitial Purchase Order | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | USACE Contractor | "Null"- Work not yet begun | "Null" - Work not yet begun | Null [Not yet complete] | Null [Not Submitted or was a site that existed prior to candidate site form ] | null [not submitted], | null [not submitted] | Null [Not yet complete] | Null [Data not yet transmitting]
| Worland | S-15 |  | N (No) | City | USDA | Existing |  |  |  |  | Nebraska | NE Mesonet | Available |  | PY2 | TO1 MT (FY20) |  |  |  |  | USACE Staff | "In-Progress" - Cultural work is underway (Station is on a cultural Task Order) and survey needs to be done. | "In-Progress" - USACE is working on NEPA and REC | MM/DD/YYY [Date that fieldwork was completed] | MM/DD/YYY | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY
| ETC. | Etc. |  |  | State | BLM | Existing - Moved more than 100 Feet |  |  |  |  | North Dakota | NDAWN | In-Progress |  | PY3 | TO3 MT (FY22) |  |  |  |  | NPS | "In-Progress SHPO/THPO" - field work is done - now is it moving through the USACE and SHPO/THPO process | "Complete - DD/MM/YYYY" - Date REC is signed.
[5 empty] | Federal | etc. | [5 empty] | South Dakota | SD Mesonet | Complete |  | PY4 | TO2 ND (FY20) |  |  |  |  | Tribe | "Complete - MM/DD/YYY" - Site is culturally cleared. Date it was complete. | Flag
[5 empty] | Tribal Lands | [6 empty] | Wyoming | Wyoming Mesonet | Removed |  | PY5 | etc. |  |  |  |  | etc.
[12 empty] | Minnesota |  |  |  | PY6
[12 empty] | Iowa |  |  |  | PY7